## Summary Mail
CMB:IVS - Bench Status (for the week ending 10/28/2016)
Highlights
- Initial Assessment conducted for the (CMB-IVS) resources newly added to bench report (of 10/24).
- At least one work item has been assigned to each individual who completed the assessment & tracking the progress.
- Total 23 tasks completed (for the month of august - October) and ratings were tracked accordingly. 15 ongoing or planned tasks.
- 11 new resources added based on latest bench report. 8 resource has got allocated to projects.
Summary
Bench Resource count & utilization Summary
| Bench Resource summary |  |  |  | Resource utilization summary
| Available | 23 |  |  |  | Utilized | 52 | Refer the attachment for more details on individual utilization
| Presented | 29 |  |  |  | Idle | 0
| US VISA | 4 |  |  | Not Available |  | 4 | Two resources allocated for projects and 2 resources in maternity leave period
| Total | 56
Bench Task Summary
| Bench Task |  | Reporting Manager/ QA lead/ Facilitator |  |  | # of Resources | Start Date ^ | Planned End Date | Status | % Completed | Comments
Ongoing & Planned Tasks
| ISTQB Foundation - December |  | NA |  |  | 15 | 2016-08-29 | 2016-12-18 | In progress | NA | Pls find the details in attachment
| ISTQB - Advanced -December |  | NA |  |  | 3 | 2016-08-29 | 2016-12-18 | In progress | NA | Pls find the details in attachment
| Writing White papers/ Blog/ Article |  | NA |  |  | 8 | Multiple | Multiple | In progress | NA | Pls find the details in attachment
| Mobility Testing Training |  | Chanaka Rathnaweera |  |  | 26 | 2016-10-19 | 2016-11-10 | Completed | NA | Ratings to be tracked
| Insurance Domain Training |  | Harshana Kuruppu |  |  | 29 | 2016-10-03 | 2016-10-05 | Completed | NA | Ratings to be tracked
| Virtusa Scrum master - September |  | SL Training Team |  |  | 5 | TBD | TBD | Not Started | NA | Waiting for schedule from training team
| Telco Domain Training |  | Nishadi / Saumika/ Pavithra |  |  | 27 | 2016-09-23 | 2016-11-10 | In progress | NA | Need to complete final session
| Capital market Domain training |  | Janani Nirasha Amarasinghe |  |  | 1 | 2016-11-22 | 2016-11-24 | Not Started | NA | PPT and evaluation criteria is complete
| Automation - Selenium Training |  | Janani Nirasha Amarasinghe |  |  | 2 | 2016-11-15 | 2016-12-02 | Not Started | NA | identified as an important area for trainings
| GLANCE - Test Automation |  | Kapila Karunaratne |  |  | 2 | 2016-10-27 | 2016-11-30 | In progress | NA | Scripting work Stared
| ICTA Development of mobile apps- RFP |  | Kapila Karunaratne |  |  | 1 | 2016-10-20 | 2016-11-19 | In progress | NA | WIP
| Banking Domain Testing Research |  |  | Pavithra Kankanamge |  | 5 | 2016-11-10 | TBD | Started | NA | complete Initial discusstion
| Web Service Testing (SoapUI) Traininig |  |  | TBD |  | TBD | TBD | TBD | Not Started | NA
| Soft Skill Development Traininig |  |  | TBD |  | TBD | TBD | TBD | Not Started | NA
| Hybrid Test Automation Framework |  | Abdhul Kareem |  |  | 1 | 2016-10-03 | 2016-11-28 | In progress | NA | Further improvement are inprogress
| Performance testing Basics training |  | Nuwan Mudalige |  |  | 1 | TBD | TBD | Not Started | NA | Identified as a new area for trainings.
| Seniorlink Project Support |  | Thushara Namal Dissanayake |  |  | 8 | 2016-10-19 | TBD | In progress | NA
Completed
| Security Testing Training- Batch 2 |  | Sheron Logitharajah/Sumith Rohana |  |  | TBD | 2016-10-26 | 2016-11-02 | Completed | NA | Batch 1 and 2 complete
| CITI Project Support |  | Pandu Thuyakontha |  |  | 1 | 2016-07-15 | 2016-08-01 | Completed | NA | Ratings received/Tracked
| PEGA Trainings |  | Gayani Sri Wickramasingha |  |  | 29 | 2016-10-06 | 2016-10-06 | Completed | NA | Ratings received/Tracked
| Presale - Telecom Ministry I&HTM System |  | Kapila Karunaratne |  |  | 2 | 2016-07-14 | 2016-08-08 | Completed | NA | Ratings received/Tracked
| CRICO Project Support |  | Thushara Namal Dissanayake |  |  | 4 | 2016-06-30 | 2016-08-10 | Completed | NA | Ratings received/Tracked
| Test Automation Training |  | Abdul Kareem |  |  | 11 | 2016-07-26 | 2016-08-11 | Completed | 100% | Ratings received/Tracked
| Presale - FMC QA Proposal |  | Rasika Suriarachchi |  |  | 3 | 2016-08-08 | 2016-08-12 | Completed | NA | Ratings received/Tracked
| Virtusa Scrum master - August |  | SL Training Team |  |  | 2 | 2016-08-10 | 2016-08-22 | Completed | 100% | Online examination is pending.
| Presale - Roche |  | Thushara Namal Dissanayake |  |  | 1 | 2016-08-10 | 2016-08-26 | Completed | NA | Ratings received/Tracked
| IVS Hiring questions preparation |  | Rasika Suriarachchi |  |  | 3 | 2016-08-08 | 2016-08-29 | Completed | 100% | Ratings received/Tracked
| Healthcare Domain Training |  | Neranjan Vidanagama |  |  | 12 | 2016-08-03 | 2016-09-08 | Completed | 100% | Ratings received/Tracked
| HealthNow - RFP |  | Thushara Namal Dissanayake |  |  | 1 | 2016-09-05 | 2016-09-16 | Completed | NA | QA approach and estimates were shared
| QA write up for NBE |  | Rasika Suriarachchi |  |  | 2 | 2016-08-25 | 2016-08-31 | Completed | NA | Ratings received/Tracked
| ISTQB Foundation - August |  | NA |  |  | 2 | 2016-07-11 | 2016-08-31 | Completed | NA | Results received/Tracked
| Medical Mutual of Ohio Proposal |  | Thushara Namal Dissanayake |  |  | 2 | 2016-09-21 | 2016-10-05 | Completed | NA | Proposal submitted
| Boston Scientific - QA Estimates |  | Thushara Namal Dissanayake |  |  | 1 | 2016-09-23 | 2016-09-28 | In progress | NA | Estimation submitted
| GCOM - DOHMH New EMR RFP |  | Harshana Kuruppu |  |  | 1 | 2016-09-13 | 2016-09-13 | Completed | NA
| BCBS - RFP |  | Thushara Namal Dissanayake |  |  | 3 | 2016-09-13 | TBD | Closed | NA | Client is not expecting QA for this
| Release Management Process RFP |  | Pulathisi Rahubedda |  |  | 1 | 2016-10-10 | 2016-10-21 | Completed | 100%
| Allianz CUBE - RFP |  | Harshana K. Kuruppu |  |  | 1 | 2016-10-10 | 2016-10-21 | Completed | 100%
| ICTA E-Services - RFP |  | Kapila Karunaratne |  |  | 1 | 2016-09-28 | 2016-10-24 | Completed | NA
| Boston Scientific - QA Strategy |  | Thushara Namal Dissanayake |  |  | 1 | 2016-10-03 | 2016-10-13 | Completed | NA | Awaiting presentation to client
| University Sessions - QA |  | Jagath Desilva |  |  | 1 | 2016-10-07 | 2016-10-19 | Completed | 100%
| QA Sales team support |  | Anjana Chandrapala |  |  | 3 | 2016-08-12 | 2016-09-09 | Completed | NA | Ratings received/Tracked
Note on G19: Not Available due to various reasons as stated in comment section. But marked as available/ presented in Bench report.

## Work tracking
Bench Work Tracking |  | Presale - Release Management Process |  |  |  |  | Presale - Medical Mutual Ohio Proposal |  |  |  |  | Allianz CUBE - RFP |  |  | Presale - CIME SBU |  |  | ICTA E-Services RFP |  |  | ICTA E-Services RFP |  |  | QA Sales team support |  |  |  |  | HealthNow - RFP |  |  |  |  | Boston Scientific - Estimation |  |  |  |  | BCBS - RFP |  |  |  |  | GCOM - DOHMH New EMR RFP |  |  |  |  | SLASSCOM Awards application |  |  |  |  | QA write up for NBE Awards |  |  |  |  | Bench management |  |  | Project Support - HealthFirst |  |  | Project Support - Senior Link |  |  | Performance testing |  |  |  | Test Automation - Basic |  |  |  |  | Domain - Healthcare |  |  |  |  | Domain - Telecom |  |  |  |  | Domain - Insurance |  |  |  |  | Training on PEGA |  |  |  |  | Security testing |  |  |  |  | Mobility testing |  |  |  |  | Test Automation |  |  |  |  | Domain - Healthcare |  |  |  |  | Web Service Testing (SoapUI)/DB2 Training preparation |  |  |  |  | Sessions on QA (Kotalawala Def academy & University of Ruhuna) |  |  |  |  | ISTQB - Foundation |  |  |  |  | ISTQB - Advanced |  |  | Virtusa Scrum master |  |  |  |  | Pre-sale - Commercial Bank RFP |  |  | MIT Process improvement |  |  | Writing White papers/ Article |  |  |  |  | Writing Blogs & News Letters |  |  |  |  | Hybrid automation framework |  |  |  |  | Create test assets - Domain A |  |  | Create test assets - Domain B |  |  | Mind mapping PEGA framework using OSCAR |  |  | GLANCE test automation project |  |  | Comments
|  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Start Date | End date | Status | Start Date | End date | Status | Start Date | End date | Status | Progress | Target End date | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date
# | Resouce Name | Presales | [59 empty] | Project Support | [5 empty] | Training participation | [43 empty] | Conduct Trainings | [14 empty] | Certifications | [12 empty] | Knowledge Management | [26 empty] | Rigor projects
1 | Mohamed Fulail | [70 empty] | Completed | 0% | 2016-08-11 | NA | Did not attend any session. Exercise Not Submitted. <Input from trainer>. | Completed | 80% | 2016-09-08 | 4 | EEC | In progress | 80% | 2016-11-10 |  | Attended both sessions but did sit for spot test of 1st session | In progress |  |  |  |  | Completed | 100% | 2016-10-06 | MAES | 16/20 | [38 empty] | Completed | 100% | 30-Jul 22-Aug |  | Pending examination from SLTT | [33 empty] | Resource has not participated to July Scrum, extended to august.
2 | Sashi Mekala De Alwis | [47 empty] | Completed | 100% | 2016-09-21 | MAES | [19 empty] | NA |  |  |  |  | Completed | 75% | 2016-09-08 | 3 | MAES | In progress | 50% | 2016-11-10 |  | Attended 1 session | [5 empty] | Completed | 100% | 2016-10-06 | EEC | 19/20 | [30 empty] | Assigned | 0% | 2016-12-31
3 | Pavithra Kankanamge | [22 empty] | Completed | NA | 2016-09-09 | MAES | [37 empty] | Completed | 2016-10-19 | 2016-10-20 |  |  |  |  | NA |  |  |  |  | Completed | 75% | 2016-09-08 | 3 | MAES | In progress | 100% | 2016-11-10 |  | Trainer of the 1st session and organiser of the training | In progress |  |  |  |  | Completed | 100% | 2016-10-06 | EEC | 18/20 | [30 empty] | In progress | 30% | 2016-12-31 | [5 empty] | Assigned | 0% | 2016-09-30 | [13 empty] | In progress | 90% | 2016-09-09 |  | Topic: Practice mindfulness toward success of the organization, Status: Inprogress | In progress | 90% | 2016-09-09 |  | Topic: Practice mindfulness toward success of the organization, Status: Inprogress
4 | Nadeeka Samanthi Wijewantha | [70 empty] | NA |  |  |  |  | NA |  |  |  |  | In progress | 100% | 2016-11-10 | [7 empty] | Completed | 100% | 2016-10-06 | MAES | 14/20 | [30 empty] | In progress | 50% | 2016-12-31 | [5 empty] | Assigned | 0% | 2016-09-30 | [8 empty] | Completed |  | 2016-09-13 | MAES | Topic: SPEAKING EYE for differently abled people to see the web content
5 | Jayasanka Nimanthi | [70 empty] | NA |  |  |  |  | NA |  |  |  |  | Assigned | 0% | 2016-11-10 |  | did not attend 2 sessions due to bad health | In progress | [8 empty] | informed will not be able to attend due to sickness | [35 empty] | Assigned | 0% | 2016-12-31
6 | Kanishka Dilrukshi Gamage | [80 empty] | Assigned |  | 2016-11-10 | [7 empty] | Completed | 100% | 2016-10-06 | EEC | 18/20 | [15 empty] | Completed | 100% | 2016-09-01 | 3 | MEAS given for interest shown, presentation skills need more work. | [15 empty] | Assigned | 0% | 2016-12-31
7 | Hasari Wasana | [80 empty] | In progress | 50% | 2016-11-10 |  | Attended 1 session | [5 empty] | Completed | 100% | 2016-10-06 | MAES | 15/20 | [5 empty] | In progress | 35% | [23 empty] | In progress | 40% | 2016-12-31 | [16 empty] | Completed | 100% | 2016-10-21 | NI | Topic: Integrating test management and risk management for the projects. Most parts of this article was taken from https://www.sqs.com/de/_download/White_Paper_Integrating_TM_and_RM_EN.pdf
8 | she has good experience tesing and she can explain process related to experience. She hashandled few member team but she did not involved in estimatons. | [66 empty] | Completed |  | 2016-09-23 | [11 empty] | In progress | 50% | 2016-11-10 |  | Attended 2 sessions | [5 empty] | Completed | 100% | 2016-10-06 | EEC | 18/20 | [30 empty] | In progress | 15% | 2016-12-31 | [5 empty] | Assigned | 0% | 2016-09-30 | [35 empty] | Self studying Apche Jmeter
9 | Dilsha Tharanga | [80 empty] | In progress | 100% | 2016-11-10 | [42 empty] | In progress | 55% | 2016-12-31
10 | Inoka Peiris | [42 empty] | In progress | 20% | 2016-09-30 | [35 empty] | In progress | 75% | 2016-11-10 |  | Attended 2 & 3 session | Completed | 100% | 2016-10-05 |  | Atttended all 3 sessions | [35 empty] | In progress | 30% | 2016-12-31
11 | Abdul Kareem | [75 empty] | Completed | NA |  |  | Could not attend all the session due to project assignment | Assigned | 0% | 2016-11-10 | [7 empty] | Completed | 100% | 2016-10-06 | MAES | 16/20 | [59 empty] | Inprogress | 80% | 2016-10-28 |  | Imrovements and enhancements are underway | [9 empty] | Inprogress | 10% | 2016-11-30
12 | Janani Nirasha Amarasingha | [13 empty] | Completed | 100% | 2016-10-24 | Complete | 100% | 2016-10-24 | Inprogress | 10% | 2016-11-19 | [58 empty] | In progress | 10% | 2016-11-10 |  | Attended 1 session | Completed | 100% | 2016-10-05 |  |  | Completed | 100% | 2016-10-06 | EEC | 18/20 | [35 empty] | Completed | 100% | 2016-12-31 | [5 empty] | Complete | 100% | 2016-09-30 | Completed | 100% | 2016-09-30 | [24 empty] | Inprogress | 10% | 2016-11-30
13 | Janna Junaideen | [80 empty] | Inprogress | 100% | 2016-11-10 |  | Missed 1 session due to work in ATP proj |  |  |  |  | Couldn’t attend due to ATP project work |  |  |  |  | Informed will not be able to attend due to work in ATP proj | [30 empty] | Inprogress | 10% | 2017-03-30
14 | Nuwan Galkissa Mudalige | [66 empty] | Inprogress | 10% | 2016-10-19 | Conducting the trainings | [11 empty] | NA |  |  | Conducting Performance trainings | [9 empty] | Allocated to Senior link proj | [76 empty] | Helping Senior Link project with 50% allocation
15 | Vidya Yohendra
16 | Shanuka Randima De Silva | [80 empty] | In progress |  |  |  | Attended 2 session | [5 empty] | Completed | 100% | 2016-10-06 | EEC | 19/20 | [5 empty] | Assigned | [24 empty] | Inprogress | 55% | 2016-12-31
17 | Shanthi Karunarathna | [63 empty] | Assigned | [26 empty] | Completed | 100% | 2016-10-06 | MAES | 16/20
18 | Viranthi Perera | [125 empty] | Inprogress | 30% | 2016-12-20 |  |  | Inprogress | 20% | 2016-12-20
19 | Yasodha Nuwanthi Rathnayaka | [125 empty] | Inprogress | 25% | 2016-12-31 |  | covered below areas Test Design Techniques Structure based or white box techniques Test Design Techniques Experience based techniques
20 | Isuri Wimarsha Boteju | [90 empty] | Completed | 100% | 2016-10-06 | MAES | 14/20 | [30 empty] | Inprogress | 45% | 2016-12-31
21 | Sahani Sulochana Alwis | [125 empty] | Inprogress | 10% | 2016-12-31
22 | Marie Dhamithree Sashikala Samaranayake | [100 empty] | Assigned | [24 empty] | Inprogress | 25% | 2016-12-31
23 | Menupa Dilushini Samarawickrama | [63 empty] | Assigned | [61 empty] | Inprogress | 10% | 2016-12-31
24 | Githmini De Alwis | [70 empty] | inprogress | 15% | [18 empty] | Completed | 100% | 2016-10-06 | MAES | 17/20 | [5 empty] | Assigned | [24 empty] | Inprogress | 15% | 2016-12-31 | [43 empty] | Train on QTP tool and Automation Framework (‘Health First’ project client interview)
25 | Tharanga Kodippiliarachchi | Inprogress | 5% | TBD | [7 empty] | Inprogress | 5% | TBD | [50 empty] | Assigned | [26 empty] | Completed | 100% | 2016-10-06 | MAES | 17/20 | [25 empty] | Inprogress | 50% | 2016-10-19 |  | Session for Def academy complete
26 | Mayuri Hewage | [100 empty] | Assigned | [24 empty] | Inprogress | 35% | 2016-12-31
27 | Devendri Vishvanatha Kumari Sarathchandra | [70 empty] | inprogress | 20% |  |  | Selenium | [15 empty] | Completed | 100% | 2016-10-06 | MAES | 16/20 | [30 empty] | Inprogress | 20% | 2016-12-31 | [16 empty] | Completed | 100% | 2016-11-07 |  | Topic: PEGA testing
28 | Kushan Wijesundara | [125 empty] | Inprogress | 20% | 2016-12-31 | [43 empty] | Currently consolidating Healthcare documents
29 | Isuri Chinthika Amarasinghe | [125 empty] | Assigned | 0% | 2016-12-31
30 | Nadeera Hettiarachchi | [63 empty] | Assigned | [61 empty] | Assigned | 0% | 2016-12-31 | [37 empty] | Inprogress | [5 empty] | Self studying on Load runner, mind mapping a PEGA framwork using OSCAR
31 | Sithumini Rajapaksha | [125 empty] | Inprogress | 20% | 2016-12-31
32 | Sashika Hiranya Samaragunaratne | [125 empty] | Assigned | 0% | 2016-12-31
33 | Dakshina Amarasinghe | [63 empty] | Assigned | [61 empty] | Assigned | 0% | 2016-12-31
34 | Viraj Jayasuriya
35 | Rasika Sanjeewanee Jayawardena | [171 empty] | Self studying on Soap UI, TestComplete to prepare for Onsite opportunity
36 | Sivakumaran Bhairavi | [168 empty] | 10% | Inprogress |  | Self Studying on Business Analysis. Awaiting BA track change .Test case writing for GLANCE
37 | Zahir Hussain Muhammed Zaumer | [171 empty] | Awaiting PM track change
38 | Lakshitha Karagaswewa | [171 empty] | Assigned to BT WLMS awaiting allocation
39 | Kusum Carmon Nanayakkara | [80 empty] | In progress | 50% | [18 empty] | In Progress | 50%
40 | Supun Gunasinghe | [165 empty] | Completed | 100%
41 | Chandima Wijebandara Athapattu
42 | Hirunika Wickramasinghe
43 | Hiroshani Ekanayaka | [125 empty] | inprogress | 25% | 2016-12-31 | [43 empty] | NTB KT Session In progress
44 | Harsha Jayawilal
45 | Heshani Subasinghe | [125 empty] | inprogress | 40% | 2016-12-31
46 | Piyumi Muthukumarana
47 | Dhammika Munasinghe
48 | Charutha Fonseka
49 | Devindya Nagahawatta | [171 empty] | Selemium training / ISTQB
50 | Shashikala Thangawelu | [133 empty] | Assigned | 0% | 2016-12-21
51 | Sheron Gerard Jeshuran Logitharajah
52 | Rinusha Wickramasinghe | [125 empty] | Assigned | 0% | 2016-12-18
52 | Hemal Nishantha | [115 empty] | Assigned | [9 empty] | Assigned
Note on FY1: Ravindra Wickramaarachchi: Comments on deviation in progress, missing timelines, level of commitment, quality of work, work duration, evaluated ratings

## Archive
Bench Work Tracking - Archived work items |  | Presale - Ministry of Telecom DI&HTM System |  |  |  |  | Presale - Medical Mutual Ohio Proposal |  |  |  |  | Presale - FMC QA Proposal |  |  |  |  | Presale - Roche |  |  |  |  | QA Sales team support |  |  |  |  | Bench management | [5 empty] | CRICO Project support |  |  |  |  | CITI Project Support | [5 empty] | Performance testing |  |  | Test Automation - Basic |  |  |  |  | Domain - Healthcare | [5 empty] | Domain- Telecom |  |  |  |  | Test Automation | [5 empty] | Security Testing |  |  |  |  | ISTQB - Foundation |  |  |  |  | ISTQB - Advanced |  |  |  |  | Virtusa Scrum master | [5 empty] | Training on PEGA |  |  |  |  | Writing White papers |  |  |  |  | Writing Blogs |  |  | Create test assets - Domain |  |  | IVS Hiring questions preparation | [5 empty] | Rigor project - H |  |  | Rigor project - I |  |  | Comments
|  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating |  | Status | Progress | Target date | Rating | Comments |  | Status | Start Date | End date | Rating | Comments | Status | Progress | Target date | Rating | Comments |  | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments |  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments |  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments |  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments |  | Status | Progress | Target date | Status | Progress | Target date
# | Resource Name | Presales | [41 empty] | Training participation | [13 empty] | Conduct Trainings | [15 empty] | Certifications | [15 empty] | Knowledge Management | [21 empty] | Rigor projects
1 | Asiri Manoja | [31 empty] | Completed | 2016-06-30 | 2016-07-22 | 3 | MEAS | [9 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource was busy with CRICO support during this period. | [66 empty] | Resource got permanently allocated to CRICO
2 | Prasadie Lakmini Dharmasena | [45 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource got allocated to a project before training starts. | [22 empty] | Assigned | 0% | 2016-08-31 | NA | Resource allocated to a project before task completion. No update mail received on the completion % before archiving the task. | [39 empty] | Resource got allocated to VTAF.
3 | Kanchana Jayalath | [45 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource took maternity leave (7/15) before training starts. | [22 empty] | Assigned | 0% | 2016-12-31 | NA | Resource took maternity leave (7/15) before training starts. No update mail received on the completion % before archiving the task. | [39 empty] | on maternity leave from 7/15
4 | Geethika Kalhari Jayasinghe | [45 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource took maternity leave (7/20) before training starts. | [22 empty] | Assigned | 0% | 2016-12-31 | NA | Resource took maternity leave (7/20) before training starts. No update mail received on the completion % before archiving the task. | [39 empty] | on maternity leave from 7/20
5 | Channa Gunasekera | [36 empty] | Completed | 2016-07-15 | 2016-08-01 | 3 | MEAS |  |  |  |  | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource got allocated to a project before training starts. | [22 empty] | Assigned | 0% | 30-AugDec | NA | Resource allocated to a project before task completion, communicated that the task will be attempted on Dec. | [39 empty] | Allocated to Citi team till end of aug, postponed the ISTQB for dec.
6 | Anushika Gunaratne | [31 empty] | Completed | 2016-06-30 | 2016-08-02 | 3 | MEAS | [9 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource was busy with CRICO support during this period. | [66 empty] | Resource got permanently allocated to CRICO
7 | Shanika Kavimini Pindeniya | [116 empty] | Attrition, Unable to contact.
8 | Rangajith Lakmal Rajakaruna | [31 empty] | Completed | 2016-06-30 | 2016-08-10 | 3 | MEAS | [9 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource was busy with CRICO support during this period. | In progress | 60% | 2016-09-08 | 3 | Resource was busy/allocated to CRICO. But still managed to come to most trainings. | [61 empty] | Resource got permanently allocated to CRICO
9 | Rashmi Pathirana | [31 empty] | Completed | 2016-06-30 | 2016-08-10 | 3 | MEAS | [9 empty] | Assigned | 0% | 2016-08-11 | NA | Could not attempt, as the resource was busy with CRICO support during this period. |  |  |  | NA | Could not attempt, as the resource was busy with CRICO support during this period. | [61 empty] | Resource got permanently allocated to CRICO
10 | Shanthiruban Balasubramaniam | [45 empty] | In progress | 75% | 2016-08-11 | NA | Resource allocated to a project before task completion. | In progress | 20% | 2016-09-08 | NA | Resource allocated to a project before task completion. | [17 empty] | In progress | 60% | 2016-08-31 | NA | Resource allocated to a project before task completion, communicated that the task will be attempted on Dec. | [39 empty] | Allocated to FLEX, postponed the ISTQB for dec. Could not attend all the sessions of automation & Healthcare trainings
11 | Dilini Liyanapatabendi | [45 empty] | Completed | 50% | 2016-08-11 | NA | Attended only 1 sessions / Exercise Not Submitted. <Input from trainer>. | In progress | 20% | 2016-09-08 | NA | Was a trainer for one session. Did not attempt as a participant. | [38 empty] | In progress |  | 2016-08-31 | NA | Resource allocated to a project before task completion. No details/status were shared before archiving. | [18 empty] | Allocated to Aetna DME Plus on 8/22 (but Start working from 8/8)
12 | Achani Wickramasinghe | Completed | NA | 2016-08-08 | 3 | MEAS | [40 empty] | Completed | 0% | 2016-08-11 | NA | Did not attend any session. <Input from trainer>. | In progress | 0% | 2016-09-08 | NA | Resource allocated to a project before task completion. See Attendance tab. | [61 empty] | Allocated to MIT Leadership QA
13 | Duminda Pathirana | Completed | NA | 2016-08-08 | 3 | MEAS | Completed | NA | 2016-08-12 | 3 | MEAS | Completed | NA | 2016-08-12 | 3 | MEAS | [35 empty] | In progress | 20% | 2016-09-08 | NA | Resource allocated to a project before task completion. See Attendance tab. | [49 empty] | Completed | NA | 2016-08-28 | 3 | MEAS | [7 empty] | Allocated to Citi ICG TTS RPA Prod Trail
14 | Kushan Amarasiri | [93 empty] | In progress |  | 2016-08-31 | NA | Interested shown on writing article on mobility automation testing. Details on topic shared. But resource allocated to a project before task completion, & communicated same. | [18 empty] | Allocated to Taylor Atlas Support from 8/22 (started 8/19)
15 | Sashika Paranamanage | [50 empty] | In progress | 50% | 2016-09-08 | NA | Resource allocated to a project before task completion. See attendance tab. | [17 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Allocated to Citi ICG TTS RPA Prod Trail
16 | Sampath Sisira Kumara | [15 empty] | Completed | NA | 2016-08-26 | 4 | EEC | [62 empty] | Assigned | 0% | 2016-09-30 | NA | Resource allocated to a project before task starts. | [29 empty] | Allocated to Seniorlink MA Elaboration
17 | Janani Nirasha Amarasingha | [77 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/status received before archiving the task. | [34 empty] | Allocated to MIT Leadership QA
18 | Neranjan Vidanagama | [25 empty] | Completed | 2016-07-05 | 2016-09-09 | 3 | MEAS | [15 empty] | Completed | 75% | 2016-08-11 | 3 | MEAS, Attended 3 sessions / Exercise Submitted. <Input from trainer>. | Completed | 100% | 2016-09-08 | NA | Coordinator/Trainer | [49 empty] | Completed | NA | 2016-08-28 | 3 | MEAS | [7 empty] | Not available in 8/22 bench report, locked to a future allocation.
19 | Nadeera Prashanthi Jayathilake | [45 empty] | Completed | 0% | 2016-08-11 | NA | Did not attend any session. Attrition, not available from 8/22 report. | In progress | 40% | 2016-09-08 | NA | Attrition, not available from 8/22 report. | [22 empty] | In progress | 0% | 2016-12-31 | NA | Communicated that this will be postponed & attempted in Dec. And Attrition, not available from 8/22 report. | [34 empty] | Attrition, not available in 8/22 bench report.
20 | Heshani Laknilu Subasinghe | [50 empty] | Assigned | 0% | 2016-09-08 | NA | Unable to contact, not available in 8/22 bench report. | [17 empty] | Assigned | 0% | 2016-08-31 | NA | Unable to contact, not available in 8/22 bench report. | [39 empty] | Unable to contact, not available in 8/22 bench report.
Archived from 8/29 - Bench Report
21 | Abdul Kareem | [50 empty] | In progress | 20% | 2016-09-15 | NA | Resource allocated to a project before task completion. See attendance tab. | [6 empty] | Completed | 100% | 2016-08-11 | 1900-01-02 | MEAS | [50 empty] | Allocated to Taylor Atlas Support (Not in 8/29 bench report)
22 | Hasini Lakmali Gunawardena | [72 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Allocated to Citi ICG TTS RPA Prod Trail (Not in 8/29 bench report)
23 | Mohomed Irshad Seyed Ahamed | [82 empty] | Assigned | 0% | 2016-09-30 | NA | Resource locked to a project before task start. | [29 empty] | Not available/presented list in 8/29 bench report (Locked)
24 | Poornada Ruwandi Amarasekara | [82 empty] | Assigned | 0% | 2016-09-30 | NA | Resource was on medical leave before task start. | [29 empty] | Not available/presented list in 8/29 bench report (On medical leave)
25 | Nimasha Ranmuthu | [72 empty] | Assigned | 0% | 2016-12-31 | NA | Resource locked to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Not available/presented list in 8/29 bench report (Locked)
26 | Lakmali Rajaguru | [82 empty] | Assigned | 0% | 2016-09-30 | NA | Attrition | [29 empty] | Not available/presented list in 8/29 bench report (Attrition)
27 | Yasitha Bandara | [82 empty] | Assigned | 0% | 2016-09-30 | NA | Resource locked to a project before task start. | [29 empty] | Not available/presented list in 8/29 bench report (Locked)
Archived from 9/5 - Bench Report
28 | Madhushika Wijenayaka | [45 empty] | Completed | 0% | 2016-08-11 | NA | Did not attend any session. Exercise Not Submitted. <Input from trainer>. | In progress | 0% | 2016-09-08 | NA | Did not attend any of the trainings | [17 empty] | Assigned | 0% | 2016-08-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Not available/presented list in 9/5 bench report. (On Maternity)
29 | Roshini Fernando | [45 empty] | Completed | 75% | 2016-08-11 | 2 | NI, Attended 3 sessions / Exercise Submitted. <Input from trainer>. | In progress | 60% | 2016-09-08 | NA | Resource allocated to a project before task completion. See attendance tab. | [27 empty] | Completed | 100% | 30-Jul 22-Aug |  | Completed online exam | [29 empty] | Allocated to Resource has requested to participate for July scrum, but all slots were full. Extended to august.
30 | Mohamed Aashik | [5 empty] | Completed | NA | 2016-08-12 | 3 | MEAS | Completed | NA | 2016-08-12 | 3 | MEAS | [30 empty] | Completed | 25% | 2016-08-11 | 1 | Attended only 1 sessions / Exercise Not Submitted. <Input from trainer>. | In progress | 60% | 2016-09-08 | NA | Resource allocated to a project before task completion. See attendance tab. | [17 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Not available/presented list in 9/5 bench report. Locked to EAG
31 | Rinusha Wickramasinghe | [45 empty] | NA |  |  |  |  | NA | [21 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Not available/presented list in 9/5 bench report. Allocated to Citi ICG TTS RPA Prod Trail
32 | Charutha Fonseka | [45 empty] | NA |  |  |  |  | NA | [21 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Not available/presented list in 9/5 bench report. Locked to BT Plusnet
33 | Wathsala Sandamali | [45 empty] | NA |  |  |  |  | NA | [21 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion. No update/details shared before archiving the task. | [39 empty] | Not available/presented list in 9/5 bench report. Locked to EAG
34 | Shamika Perera | [45 empty] | NA |  |  |  |  | NA | [31 empty] | Assigned | 0% | 2016-09-30 | NA | Resource allocated to a project before task starts. | [29 empty] | Not available/presented list in 9/5 bench report. Allocated to Citi ICG TTS RPA Prod Trail
Archived from 9/20 - Bench Report
35 | Nipun Suriyaarachchi | [72 empty] | In progress | 80% | 2016-12-31 | NA | Resource allocated to a project before task completion | [39 empty] | Not available/presented list in 9/20 bench report. Allocated to Senior Link
36 | Ruwanthi De Silva | [72 empty] | Assigned | 0% | 2016-12-31 | NA | Resource allocated to a project before task completion
37 | Kusum Carmon Nanayakkara | [93 empty] | Completed | 100% | 42622 | MAES | Topic: An insight into mobile testing and its latest testing challengers | [18 empty] | Not available/presented list in 9/20 bench report. Allocated to CITI
38 | Sheron Gerard Jeshuran Logitharajah | [67 empty] | Assigned | 0% | 42639 |  | Assigned to create PPTs on different aspect of security testing, Task not completed since allocated to project. Not in Bench report from 9/19
39 | Zahir Hussain Muhammed Zaumer | [72 empty] | Assigned | 0% | 2016-12-31
Archived from 9/26 - Bench Report
40 | Selvatharshini Selvanayagam | [64 empty] | NA |  |  |  |  | NA |  |  | In progress | 2% | 2016-12-31 |  | Resource allocated to a project before task completion | [39 empty] | Not available/presented list in 9/26 bench report. Allocated to Crico | [16 empty] | Self Studying on Selenium
41 | Geeshani Madurangi Gunathilaka | [72 empty] | Completed | 100% | 2016-09-25 | 4 | 72.5% marks obtained | [39 empty] | Not available/presented list in 9/26 bench report. Allocated to Fedex
42 | Anjula Gimhani Guruge | [82 empty] | Assigned | 0% | 42643 | [8 empty] | Assigned | 0% | 42664 |  | Topic to be decided | [18 empty] | Not available/presented list in 9/26 bench report. Has been moved to attrition list
Archived from 10/03 - Bench Report
43 | Nirmana Gunasekara | [5 empty] | In progress | 100% | 42648 |  | QA approach was given. Assigned to HealthFirst Project
44 | Maduri Nisansala Jayawickrama
45 | Dulani Eranthika Perera | [72 empty] | In progress | 35% | 2016-12-31
46 | Wageesha Lakshan | [61 empty] | Completed | 80% | 42593 | 3 | Attended 3 sessions. Excercise submitted. | [6 empty] | In progress | 10% | 2016-12-31
47 | Dilusha Lakmali | [116 empty] | Attrition risk
48 | Nisadi Irushani Wanigabadu | [20 empty] | Completed | NA | 2016-09-09 | MAES | [26 empty] | Completed | 80% | 2016-09-08 | 3 | MAES |  | In progress | 100% | 2016-11-10 |  | Allocated to NTB - CRM implementation’ | [55 empty] | BCBS RFP was started but did not continue. Assigned to a project
Archived from 10/12 - Bench Report
49 | Sujitha Pathmanathan | [56 empty] | In progress | 50% | 2016-11-10 |  | Attended 1 session | [16 empty] | Inprogress | 10% | 2016-12-31 | [12 empty] | Allocated to HealthFirst Project | Completed | 100% | 2016-09-21 |  | News letter on AIG CashApp project , awaiting the rating by Nilendra | [18 empty] | Allocated to HealthFirst
50 | Ruwanthi De Silva | [72 empty] | Assigned | 0% | 2016-12-31 | [13 empty] | Complete |  | 2016-10-06 | MAES | 17/20 | [23 empty] | Allocated to Gowireless
Archived from 10/12 - Bench Report
51 | Viduranga Gunarathna | [88 empty] | Completed | 100% | 42649 | MAES | 10/20 - MAES | [23 empty] | Allocated to HealthFirst
52 | Thisara Madushanka Ranasinghe | [116 empty] | Allocated to HealthFirst
53 | Kavija Senevirathne | [72 empty] | Assigned | 0% | 2016-12-31 | [41 empty] | Allocated for Micros
54 | Chamindi Kaldera | [116 empty] | Allocated for Micros
Archived from 10/24 - Bench Report
55 | Nadeesha Hansanie Hettiarachchi | [72 empty] | Inprogress | 10% | 2016-12-31 | [41 empty] | Allocated to SeniorLink
56 | Piyumi Jayasinghe | [116 empty] | Allocated for SriLankan
57 | Mawroof Manas | [116 empty] | Activity: Self studying on improving Jmeter knowledge Locked for CITI- turkey
58 | Chathurika Nethmini Senanayake | [56 empty] | Assigned |  | 2016-11-10 | [13 empty] | Assigned | 0% | 2016-12-31 | [41 empty] | Locked for COVANCE
59 | Yvonne Jayaweera | [56 empty] | In progress | 50% | 2016-11-10 |  | Attended 1 session. 1st session was conducted before bench | [11 empty] | In progress | 30% | 2016-12-31 | [13 empty] | Completed | 100% | 2016-10-06 | EEC | 18/20 | [23 empty] | Locked for COVANCE
60 | Rinusha Wickramasinghe | [54 empty] | Helping HealthFirst Proj | [5 empty] | Helping HealthFirst Proj | [55 empty] | Locked for PenFend
61 | Saumika Aberathna | [20 empty] | Completed | NA | 2016-09-09 | MAES | [26 empty] | Completed | 100% | 2016-09-08 | 4 | EEC |  | In progress | 100% | 2016-11-10 |  | Conducted the training on 29th Sep | [27 empty] | Completed | 100% | 2016-10-06 | MAES | 15/20 | [23 empty] | Worked on BCBS -RFP until client decided not to have QA Locked for Browns
62 | Premkumar Premje | [56 empty] | In progress | 50% | 2016-11-10 |  | Attended 1 session | [11 empty] | In progress | 20% | 2016-12-31 | [41 empty] | Allocated to HealthFirst
Archived from 11/03 - Bench Report
Bench Work Tracking |  | Presale - Release Management Process |  |  |  |  | Presale - Medical Mutual Ohio Proposal |  |  |  |  | Allianz CUBE - RFP |  |  | Presale - CIME SBU |  |  | ICTA E-Services RFP |  |  | ICTA E-Services RFP |  |  | QA Sales team support |  |  |  |  | HealthNow - RFP |  |  |  |  | Boston Scientific - Estimation |  |  |  |  | BCBS - RFP |  |  |  |  | GCOM - DOHMH New EMR RFP |  |  |  |  | SLASSCOM Awards application |  |  |  |  | QA write up for NBE Awards | [5 empty] | Bench management |  |  | Project Support - HealthFirst |  |  | Project Support - Senior Link |  |  |  | Performance testing |  |  |  | Test Automation - Basic |  |  |  |  | Domain - Healthcare |  |  |  |  | Domain - Telecom |  |  |  |  | Domain - Insurance |  |  |  |  | Training on PEGA |  |  |  |  | Security testing |  |  |  |  | Mobility testing |  |  |  |  | Test Automation | [5 empty] | Domain - Healthcare |  |  |  |  | Sessions on QA (Kotalawala Def academy & University of Ruhuna) |  |  |  |  | ISTQB - Foundation |  |  |  |  | ISTQB - Advanced |  |  | Virtusa Scrum master |  |  |  |  | Pre-sale - Commercial Bank RFP |  |  | MIT Process improvement |  |  | Writing White papers/ Article |  |  |  |  | Writing Blogs & News Letters |  |  |  |  | Hybrid automation framework |  |  |  |  | Create test assets - Domain A |  |  | Create test assets - Domain B |  |  | Mind mapping PEGA framework using OSCAR |  |  | GLANCE test automation project |  |  | Comments
|  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments |  | Status | Start Date | End date | Status | Start Date | End date | Status | Start Date | End date |  | Status | Progress | Target End date | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Participation % | Target end date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments |  | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Rating | Comments | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date | Status | Progress | Target date
# | Resouce Name | Presales | [60 empty] | Project Support | [6 empty] | Training participation | [44 empty] | Conduct Trainings | [9 empty] | Certifications | [12 empty] | Knowledge Management | [26 empty] | Rigor projects
28 | Anjula Alahakoon | [82 empty] | Assigned | 38% |  |  |  | Completed | 30% | 2016-10-05 |  | Attended 1 session after listing under Bench | Completed | 100% | 2016-10-06 | MAES | 16/20 | Assigned |  |  |  |  | Assigned | 20% | [19 empty] | Inprogress | 40% | 2016-12-31 | [43 empty] | Allocated for Siemens TCTP for 2 weeks from 10/24 -11/05
45 | Hansana Mendis | [107 empty] | Assigned | [15 empty] | Assigned | 0% | 2016-12-31
25 | Marie Dhamithree Sashikala Samaranayake | [102 empty] | Assigned | [20 empty] | Inprogress | 25% | 2016-12-31
39 | Niluka Monnankulama | [123 empty] | Assigned | 0% | 2016-12-31
4 | Sabithini De Silva | [72 empty] | NA |  |  |  |  | Completed | 80% | 2016-09-08 | 3 | MAES | In progress | 50% | 2016-11-10 |  | Attended 1 session. Could not attend 2nd session due to Project allocation | [5 empty] | Completed | 100% | 2016-10-06 | MAES | 13/20 | [26 empty] | Assigned | 0% | 2016-12-31
1 | Thushari Pinnaduwa | [72 empty] | Completed | 100% | 2016-08-11 | 4 | EEC, Attended all 4 sessions / Exercise Submitted. <Input from trainer>. | Completed | 100% | 2016-09-08 | 3 | MAES | Assigned | 0% | 2016-11-10 | [38 empty] | Completed | 100% | 2016-08-31 | 4 | score of 77.5% |  |  |  | Assigned | 0% | 2016-09-30 | [35 empty] | In Maternity leave
3 | Harini Kandambi | [5 empty] | Completed | 100% | 2016-10-05 |  | QA approach was given. Waiting feed back | [17 empty] | Completed | 100% | 2016-09-16 | MAES |  | Completed | 100% | 2016-09-28 | [17 empty] | Completed | NA | 2016-09-02 | 3 | MEAS |  | Completed | 2016-08-24 | 2016-11-01 | [11 empty] | Completed | 100% | 2016-08-11 | 2 | NI, Attended all 4 sessions / Exercise Not Submitted. <Input from trainer>. | Assigned | 0% | 2016-09-08 | NA | Not appilcable | In progress | 50% | 2016-11-10 |  | Attended 2 sessions. Could not attend 2nd & 3rd session due to presale work | In progress |  |  |  | Could not attend all the trainings as allocated to Bos Scientific QA strategy creation | Completed | 100% | 2016-10-06 | NA | Marked papers
Note on DP1: Ravindra Wickramaarachchi: Comments on deviation in progress, missing timelines, level of commitment, quality of work, work duration, evaluated ratings
Note on FT75: Ravindra Wickramaarachchi: Comments on deviation in progress, missing timelines, level of commitment, quality of work, work duration, evaluated ratings

## Initial Assessment
Resource Name | Questions/ Initial Assessment
| Availability | Availability Comment(s) | Virtusa Experience | Onsite Experience | Primary Specialty | Other Specialty | Primary Domain/ Experience | Secondary Domain/ Experience | Prior Experience in Presales | Prior Experience in Trainings | Trainings conducted/Areas | Existing Certificates | Technical Experience | Career plans | Interests | Concerns/notes
Rangajith Lakmal Rajakaruna | Partially available | Supporting CRICO - end date 07/15 | Total 5 yrs., worked in BT, Micros, MIT | None | Manual Testing | Mobility testing, Telco, Capital market, Hospitality | Telcom-1yrTo3yrs | BFS-1yrTo3yrs | Yes-3to6 | Yes-PrjLvlOnly>10 | Telco, Capital market, Hospitality domain areas | None | Oracle/SQL DB testing | Getting an allocation to a lead role | Learning Performance/Automation testing's, next level leadership skills | having US visa, not utilized 1.5 years,CRICO support , 30th June, 15 July
Dilini Liyanapatabendi | Available | White paper writing, ISTQB Foundation | Total 6 yrs., worked in Aetna, BT, Covance | None | Manual Testing | Healthcare, Insurance and Telco, Agile 3 years experience | Healthcare-3yrTo5yrs | Telcom-1yrTo3yrs | None | Yes-3<PrjLvlOnly>6 | Healthcare - Medical Management & AVA, Telco | Virtusa Scrum master | Oracle/SQL DB testing, ETL testing | Getting an allocation to a lead role | Mobility Testing, Learning Performance/Automation testing's, next level leadership skills | Planning to write paper first draft 15th July, ISTQB Foundation - end of August
Neranjan Vidanagama | Available | Bench management. | Total 6 yrs., worked in Aetna for the entire duration | None | Manual Testing | Sound knowledge/experienced on CMMI practices, Healthcare domain specialist, JCL/ETL/EDI Testing | Healthcare>5yrs | None | Yes-3to6 | Yes-PrjLvlOnly>10 | Healthcare - Medical Management & Claims domains | None | Rumba/DB2 for JCL & ETL testing (COBOL), EDI (ANSI 837) testing | Exploring onsite opportunities | Mobility Testing, Learning Performance/Automation testing's | Looking for onsite opportunities
Nadeeshani Chathurika | Unavailable | Working in Veracode |  | None
Praneeth Asanka Perera | Unavailable | Allocated to Covance |  | None
Thushari Pinnaduwa | Available | ISTQB Foundation - August | Total 6 yrs., worked in Edex, ICTA, HMSA, Network rail, Taller, Ironmountan, MetLife | None | Manual Testing | Performance testing ( J meter ) | Telcom<1yr | Healthcare<1yr | Yes<3 | Yes-PrjLvlOnly<3 | Trainings conducted on manual testing | None | SOPE UI, SQL DB testing | Engaging with specialty testing activities | Mobility testing, test automation | Will be on maternity leave end of October
Kanchana Jayalath | Unavailable | On maternity leave from 15th July, ISTQB Foundation - December | Total 8 yrs., worked in PNO, FIS, P&W, NYL, AIG | None | Manual Testing | Performance testing ( J meter ) | Insurance-1yrTo3yrs | BFS-3yrTo5yrs | Yes-3to6 | Yes-PrjLvlOnly>10 | Trainings conducted on manual testing, on Insurance and BFS | None | Data migration testing | Engaging with specialty testing activities | Mobility testing, | Will be on maternity leave end of July
Shanika Kavimini Pindeniya | Unavailable | Attrition
Prasadie Lakmini Dharmasena | Available | ISTQB Foundation - August | Total 4 yrs., worked in VTAF, Micros, Veracode | >6month | Automation | Manual testing, Mobility test automation | BFS<1yr | None | None | Yes-PrjLvlOnly<3 | Trainings conducted on test automation | None | API testing, SQL DB testing | Getting an allocation to a lead role | learning more on manual testing
Heshani Subasinghe | Partially available | ISTQB Foundation, Will be available 11AM to 4PM for next 2 months due to medical condition | Total 4 yrs., worked in Siemens, McDonalds, Gowireless, BT WLMS, Alere | None | Manual Testing | Mobility testing, Restaurants, Insurance, Healthcare, Telco | Healthcare-1yrTo3yrs | BFS-1yrTo3yrs | None | Yes-PrjLvlOnly<3 | Insurance, Healthcare, Telco domain training | None | SQL Server DB testing | Engaging with specialty testing activities | Learning Performance/Security/Automation testing | Under medical treatment for back pain
Chandima Karunatillake | Available |  | Total 6 yrs., worked in Aetna (2mnts), HC Pro (2 mnts), MIT (1 mnt), Akura (3yrs), NYL (1mnt) | None | Manual Testing | Some experience on SOUP UI | Insurance<1yr | BFS<1yr | None | Yes-PrjLvlOnly<3 | AKURA | None | MySQL/Oracle DB testing | Getting a billable allocation | Interested in doing ISTQB | Planning to do ISTQB Foundation (by end of August)
Mohamed Fulail | Unavailable | planning to do Virtusa Scrum Master | Total 12 yrs, worked in Alere/PCMS, IAE, FDMS, McDonalds, Thomson Reuters, NYL, Aetna, BT AIG, EAG | None | Manual Testing | Performance testing, Healthcare, Aroengine, Enterprise apps | Healthcare-3yrTo5yrs | ERP | Yes-3to6 | Yes-PrjLvlOnly<3 | SQA trainings | None | SQL redgate DB comparison testing | Going to the next level | Becoming a domain expert in healthcare
Kalhari Jayasinghe | Unavailable | Maternity leave starts 7/20 - ISTQB Foundation (in December) | Total 3.5 yrs, worked in NYL during the entire period | None | Manual Testing | Pega testing, SQL DB Validations | Insurance-3yrTo5yrs | None | None | Yes-PrjLvlOnly<3 | Trained new joiners' to the NYL projects | None | SQL DB Testing | Getting a billable allocation after returning from maternity leave. | Interested in Mobility, and learning different domain areas | Planning to do ISTQB Foundation (in December)
Madhushika Wijenayaka | Available | ISTQB Foundation | Total 5 yrs, worked in Aetna, CRICO,, MetLife | None | Manual Testing | Healthcare domain, Agile 1 years experience | Healthcare-3yrTo5yrs | Insurance<1yr | None | Yes-3<PrjLvlOnly>6 | Healthcare domain KTs | None | None | Engaging with specialty testing activities | Test Automation, Performance testing | Will be on maternity leave end of August
Maheesha Seneviratne | Available
Shanthiruban Balasubramaniam | Available | ISTQB Foundation | Total 6 yrs., worked in Aetna (2 yrs.), Flex (2 yrs.), Sri Lankan (6 mnts), Tailor (3 mnts) | None | Manual Testing | Localization testing | Healthcare<1yr | None | Yes<3 | Yes-3<PrjLvlOnly>6 | Trained interns in flex | None | SQL Server/Oracle (both on previous companies) | Getting a billable allocation (need stretched role - SE) | Interested in java scripts/ Selenium | Planning to do ISTQB Foundation (by end of August)
Channa Gunasekera | Available | ISTQB Foundation | Total 8 yrs., worked in EAG, Healthfirst | None | Manual Testing | ERP domain testing, patch testing | ERP | Healthcare<1yr | Yes<3 | Yes-Prj&Org>10 | Legacy apps, ERP domain | None | Data migration testing | Getting more knowledge on Healthcare domain, allocating to a healthcare related project | learning mobility testing/performance /automation | ISTQB Foundation
Rashmi Pathirana | Available | Supporting CRICO - end date 07/15 | Total 10 yrs., Worked in Aetna, FDC, Telerex, Healthfirst | None | Manual Testing | Test Automation, Healthcare | BFS>5yrs | BFS<1yr | Yes-3to6 | Yes-PrjLvlOnly>10 | Trainings conducted on healthcare domain | None | SQL DB testing | Getting an allocation which support for the next level | Selenium Automation
Anushika Gunaratne | Available | Supporting CRICO - end date 07/15, ISTQB Foundation - December | Total 8 yrs., Worked in Thomson Automation, Aetna, Iron mountain | None | Manual Testing | Healthcare domain, Agile 2 years experience | BFS>5yrs |  | None | Yes-PrjLvlOnly>10 | Trainings conducted on healthcare domain | None | None | Getting an allocation to a lead role | Mobility testing | Expecting to leave office by 7PM for next 6 months due to a personal reason.
Asiri Manoja Hewa Wellalage | Available | Supporting CRICO - end date 07/15, ISTQB Advance - December | Total 6 yrs., Worked in Thomson Reuters, City, FDC, Duo Software | None | Manual Testing | BFS domain and Pega | BFS-3yrTo5yrs |  | Yes-3to6 | Yes-PrjLvlOnly>10 | Trainings conducted on BFS domain & Pay TV industry | ISTQB - Foundation | ETL testing, SQL DB testing | Getting an allocation which support for the next level | Mobility testing | Expecting to leave office by 7.30PM for next 6 months due to a personal reason.
Nadeera Prashanthi Jayathilake | Available | ISTQB Advance - December, Agile training | Total 4 yrs., Worked in Aetna, FDC, AIG | None | Manual Testing | Healthcare domain | BFS-1yrTo3yrs | Insurance<1yr | None | Yes-3<PrjLvlOnly>6 | Trainings conducted on healthcare, Insurance domain | ISTQB - Foundation | ETL testing, Data migration testing | Getting an allocation to a lead role | Test Automation, Agile training | Expecting to leave office by 5 PM for next 3 months due to a personal reason.
Roshini Fernando | Available | planning to do Virtusa Scrum Master | Total 9 yrs., worked in BT, Aetna, Telerex, Covance, Thomson's, P&O, Seamen's | None | Manual Testing | Data migration, UI testing | Telcom-1yrTo3yrs | Insurance-1yrTo3yrs | None | Yes-PrjLvlOnly>10 | Project level trainings | None | SQL DB/ Data Migration Testing | Getting a billable allocation, playing stretch role (lead) | Interested in Mobility testing | AI > Virtusa Scrum Master (July Batch)
Harini Kandambi | Available | Polaris GIP integration | Total 7 yrs., worked Aetna, IAE, NYL, Micros, Matindoors | >6month | Manual Testing | Healthcare domain | Healthcare-3yrTo5yrs | Telcom-3yrTo5yrs | Yes<3 | Yes-6<PrjLvlOnly>10 | Trainings conducted on healthcare and telco domain | ISTQB - Foundation | SQL DB/ Data Migration Testing, ETL testing | Getting an allocation to a project focusing on next level stills | Test Automation, Agile training | Will be on maternity leave in November
Mohamed Aashik | Available | Pega test strategy creation, Virtusa Nexstar, ISTQB Foundation - Dec | Total 6 yrs., worked City, BT, Phillips, Telerx | >1yr | BPM Testing | Manual testing | Healthcare-3yrTo5yrs | BFS<1yr | Yes-3to6 | Yes-Prj&Org>10 | Trainings conducted on healthcare and Pega | None | Backend DB testing | Looking for onsite opportunity | BPM, Mobility testing | Having US visa
Abdul Kareem | Available | Automation training | Total 6 yrs., worked Aetna, Pearson | None | Automation | Manual testing | Healthcare-3yrTo5yrs | Edu | None | Yes-3<Prj&Org>6 | Training conducted on Healthcare and automation | ISTQB - Foundation | None | To be an automation expert | Mobility automation | Having US visa
Achani Wickramasinghe | Available | NDI presale, ISTQB Foundation | Total 8 yrs., worked in MIT, P&O, Teller, ITCA, Vista, Iron mountain | None | Manual Testing | Capital market domain | BFS-3yrTo5yrs | None | Yes-3to6 | Yes-PrjLvlOnly>10 | Training conducted on Capital market, Test design | None | SQL DB Testing | Getting an allocation to a lead role | Middleware testing, Mobility testing
Nisadi Irushani Wanigabadu | Available | ISTQB Foundation | Total 10 yrs., worked in BT, MIT | None | Manual Testing | Telco domain | Telcom>5yrs | BFS<1yr | Yes-3to6 | Yes-6<PrjLvlOnly>10 | Training conducted on Telco domain | None | Migration testing | Getting an allocation to a project focusing on next level stills | Leadership stills development, Security testing | Expecting to leave office by 5 PM for next 6 months due to a personal reason.
Duminda Pathirana | Available | NDI presale, Middleware testing | Total 8 yrs., worked in Aetna, P&O, MIT, ICTA, Telor | None | Manual Testing | Performance testing ( J meter ), Mobility testing, Security testing | BFS>5yrs | Healthcare-1yrTo3yrs | Yes-6to10 | Yes-PrjLvlOnly>10 | Training conducted on Capital market, Share point | CISI | ETL Testing, SQL/mySQL/DB2 DB testing, Migration testing | Looking for onsite opportunity | Security testing, Backend testing | Having US visa
Anuradha Rathnayake | Available | ISTQB Foundation | Total 4 months, no project experience | None | Manual Testing | No | None | None | None | None | None | ISTQB - Foundation | None | Getting an allocation to a project | Test Automation
Sabithini De Silva | Available | Available | Total 3.5 yrs., worked in Aetna, NYL, AIG, EAG | None | Manual Testing | SQL DB Testing | Insurance<1yr | Healthcare<1yr | None | None | None | Virtusa Scrum master | SQL DB Testing | Getting a billable allocation | Automation | Planning to do ISTQB Foundation (in December)
Hasini Lakmali Gunawardena | Available | Available | Total 4.7 yrs., worked in Aetna (1 yr.), BT (2.5 yrs), Citi (1 yr) | None | Manual Testing | Telco domain | Telcom-1yrTo3yrs | BFS<1yr | None | Yes-6<Prj&Org>10 | Training conducted on Banking domain | None | SOPE UI, SQL DB testing | Getting a billable allocation | Selenium Automation | Planning to do ISTQB Foundation (in December)
Saumika Aberathna | Available | ISTQB foundation | Total 8 yrs, Thomsan, Metavante, Philips, BT | >6month | Manual Testing | Automation | BFS-1yrTo3yrs | Telcom-1yrTo3yrs | Yes<3 | Yes-6<PrjLvlOnly>10 | Training conducted on Healthcare | None | None | Getting an allocation to a project focusing on next level stills | Mobility testing | Expecting to leave office by 7PM for next 6 months due to a personal reason.
Pavithra Kankanamge | Available | Writing a blog, Virtusa Scrum master | Total 10 yrs., worked in BT (8 yrs.), Aetna (3mths), Ironmountain (6mths) | None | Manual Testing | Telco domain | Telcom>5yrs | Healthcare<1yr | Yes<3 | Yes-Prj&Org>10 | Onboarding to new jonees | None | SOPE UI, SQL DB Testing | Getting a billable allocation | Management, Research | Need to leave early to feed the baby. Can work late hours from home.
Sashika Paranamanage | Available | ISTQB Foundation | Total 6 yrs., ERA Insight (5.5yrs), Covance (6 mnts) | None | Manual Testing |  | Internal Application | None | Yes<3 | Yes-PrjLvlOnly>10 | ERA internal application trainings | None | SQL DB Testing | Getting a billable allocation | Automation, Grab different domain knowledge. | Planning to do ISTQB Foundation (in December)
Maduri Jayawickram | Available | ISTQB Foundation | Total 6 yrs., Siemens (3 yrs.), Veracode (1 yr.), USA Today (6 mnts.), Covance (6 mnts) | None | Manual Testing |  | Siemens | Security | None | Yes-6<PrjLvlOnly>10 | Siemens internal trainings | None | SQL DB Testing | Getting a billable allocation | Automation | Planning to do ISTQB Foundation (in December)
Sashi De Alwis | Available | ISTQB Foundation | Total 4 yrs., MDS (7mnts), NYL (1.5yrs), Crico (5 mnts), Covance (6 mnts), Aetna (6 mnts) | None | Manual Testing |  | Healthcare-3yrTo5yrs | Telcom<1yr | Yes<3 | None | None | None | PUTI, TOAD, SQL DB Testing | Getting a billable allocation | Automation | Planning to do ISTQB Foundation (in December)
Harshani Nilushika Lakmali | Unavailable | Allocated to a project before Initial Assessment
Nadeeka Samanthi Wijewantha | Available | Virtusa Scrum Master | Total 8yrs., BT(3yrs.), NYL (8mths.) Pearson (1 yr.), Philips (8 mnts), McDonalds (4 mths.) | None | Manual Testing | Accessibility testing | Telcom-3yrTo5yrs | Healthcare-1yrTo3yrs | Yes<3 | Yes-3<PrjLvlOnly>6 | Accessibility trainings | None | SOUP UI, SQL DB Testing | Getting a billable allocation | Mobility | Virtusa Scrum Master
Mohomed Irshad Seyed Ahamed | Available | Virtusa Scrum master | Rejonee (3yrs prior experience + 6 yrs in Orange HRM) | None | Automation | HR Domain, Performance testing ( J meter ), PHP, SQL, Linux | None | None | None | None | None in Virtusa - Automation (selenium training) in previous company | None | PHP, SQL, JAVA-Selenium, Java Scripting, Linux scripting | Getting a billable allocation | Performance | Interested in brushing up QA knowable as the resource was out of touch from QA field and has worked as a Project Lead.
Shanuka Randima De Silva | Available |  | Total 5.8 yrs ( BT, Aetna, UTC, NYL, Taylor, NetJet) | None | Manual Testing | None | Insurance-1yrTo3yrs |  | None | None | Selenium trainings attended outside of Virtusa | Virtusa Scrum master | SQL DB Testing | Getting a billable allocation in automation project | Automation - selenium | Planning to do ISTQB Foundation (in December)
Sampath Sisira Kumara | Available | Roche Presale - 26th end date, Virtusa Scrum Master Training | Total 10 yrs, Aetna, Mettawante, NYL, Philips, Covance | 6to1yr | Manual Testing | Performance testing | Insurance>5yr | Healthcare-1yrTo3yrs | Yes-3to6 | Yes-PrjLvlOnly>10 | Training conducted on QC, Insurance domain | None | SQL DB Testing | Getting a billable allocation | Performance testing, ETL testing
Kusum Carmon Nanayakkara | Available | Mobility training | Total 5 yrs, Covance, UTC, MDS, MIT, CDB | None | Manual Testing | Healthcare and Telco domain | Telcom>5yrs | Healthcare-1yrTo3yrs | Yes<3 | Yes-3<Prj&Org>6 | Training conducted on Healthcare | ISTQB Fun. + Virtusa Scrum Mstr. | SQL DB testing | Getting an allocation to a project focusing on next level stills | Mobility testing
Selvatharshini Selvanayagam | Available | ISTQB Foundation | Total 3 yrs., Ironmountan (1yr.), BT (1yr.), Covance (3 mths.) | None | Manual Testing |  | Telcom-1yrTo3yrs | Healthcare<1yr | None | None | None | None |  | Getting a billable allocation
Kushan Amarasiri | Partially available | Involved in Jagath technical initiation (Not confirme). | Rejonee (5 months prior in dell Secure work + 6 yrs in Pearson) | None | Automation | Web services (SOUP UI), Multiple automation (selenium, Robot framework, UFT/QTP) | None | None | None | Yes-6<PrjLvlOnly>10 | Selenium | None | SOUP UI, Selenium, Robot framework, UFT/QTP | Getting an allocation in technical role | Mobility | Writing an article, Interested to do automation training APM mobility automation testing.
Zahir Hussain Muhammed Zaumer | Available | ISTQB Foundation Dec, Healthcare training. | Total 6.5 yrs. (BT 2yrs., Aetna 2.5 yrs., Person 1 yr., Covance 1 yr.) | None | Manual Testing |  | Healthcare-1yrTo3yrs | Telcom-1yrTo3yrs | None | Yes-6<PrjLvlOnly>10 | Aetna, Covance internal project trainings | Virtusa Scrum master | SOUP UI, SQL DB Testing | Getting a billable allocation, Moving to PM track | Automation | Slightly busy till Sep 12 (Hajj festival), completely free after that.
Jayasanka Nimanthi | Available | Maternity leave starts October. ISTQB Foundation (December). | Total 5 yrs., worked in NYL for the entire duration | None | Manual Testing | Insurance (Claims) domain | Insurance>5yr | None | None | Yes-PrjLvlOnly>10 | Claims | None | SOUPUI/Web Services, Data Migration testing
Rinusha Wickramasinghe | Available | ISTQB Foundation | Total 10 yrs, Worked in Aetna, Thompson Routers, Mettawante, City, FDC, Gcom | None | Manual Testing | Test Automation, BFS | BFS-3yrTo5yrs | Healthcare-1yrTo3yrs | None | Yes-6<PrjLvlOnly>10 | Training conducted on BFS and Healthcare domain | None | None | Getting a billable allocation | Automation
Janani Nirasha Amarasingha | Available | MIT Process improvement , ISTQB Advance | Total 8 yrs, MIT, MacDonald's, IBM, Thompson | None | Automation | Capital market domain | BFS>5yrs | None | Yes<3 | Yes-Prj&Org>10 | Training conducted on Capital Market domain, Automation, On boarding | ISTQB - Foundation | Verifix automation | Getting a onsite opportunity | Selenium Automation | Having US visa
Nirmana Gunasekara | Available | Writing white paper | Total 7 yrs., Sahana (2 mnts), Aetna (6+) | None | Manual Testing | Hammer IVR Automation | Healthcare>5yrs | None | Yes<3 | Yes-3<PrjLvlOnly>6 | Aetna data creation & requesting, channel domain trainings | None | SQL DB Testing | Exploring onsite opportunities | Performance, Mobility | Finding onsite opportunities.
From 8/22 - Bench Report
Charutha Fonseka | Available | ISTQB Foundation (December 4th) | Total 5 months (Info MC) | None | Manual Testing | None, fresher | Healthcare<1yr | None | None | None | None. | None | SQL DB Testing | Getting a billable allocation | Automation | None
Poornada Ruwandi Amarasekara | Available | Virtusa Scrum Master (Sep?). Requested deallocation due to health condition, might be go on medical leave soon. | Total 5.3 yrs (MIT2.5yrs, NYL 2yrs, Crico 4mnts) | None | Manual Testing | None | Insurance-1yrTo3yrs | BFS-1yrTo3yrs | None | Yes-PrjLvlOnly>10 | Project level trainings on premium calculation, benefit change | None | SOUP UI |  | Performance, Automation | Requested deallocation due to health condition, might be go on medical leave soon.
Kanishka Dilrukshi Gamage | Available | ISTQB Advance (December 4th), Healthcare training | Total 5.5 yrs., worked in Aetna for the entire duration | None | Manual Testing | Domain | Healthcare>5yrs | None | None | Yes-PrjLvlOnly>10 | Project level trainings on provider & member domains | ISTQB Fun. + Virtusa Scrum Mstr. | SOUP UI, SQL DB Testing | Getting a billable allocation | Mobility | None
Wathsala Sandamali | Available | ISTQB Foundation (December) | Total 5 months (worked in rigor only - Robert framework) | None | Automation | Robert framework | None | None | None | None | None | None | None | Getting a billable allocation | Automation | None
Nimasha Ranmuthu | Available | ISTQB Foundation (December) | Total 5 months (worked in rigor only - Robert framework) | None | Automation | Robert framework | None | None | None | None | None | None | None | Getting a billable allocation | Automation - Selenium | None
Shamika Perera | Available | Virtusa Scrum Master (Sep?) | Total 1yr (MIT, Sri Lankan) | None | Manual Testing | None | Reservation | None | None | None | None | None | None | Getting a billable allocation | Automation | None
Udani Hapuarachchi | Unavailable | On maternity leave starting 8/24.
Sheron Gerard Jeshuran Logitharajah | Available | Security testing training | Total 3.5yrs (Siemens 6mtns, BT-3yrs) | None | Security testing | Performance | Telcom-3yrTo5yrs | None | Yes<3 | Yes-Prj&Org>10 | Security testing | Virtusa Scrum master | Security, Performance | Getting a billable allocation in Performance or security | Automation | None
Hasari Wasana | Available | Writing an article | Total 4yrs (Aetna 2yrs, FDC 3mnts, Iron mountain 1yrs) | None | Manual Testing | Performance, Web services | Healthcare-1yrTo3yrs | Diversify | None | Yes-3<PrjLvlOnly>6 | Project level trainings | None | SOUP UI, Rest Client, SQL DB Testing | Getting a billable allocation | Automation | Working on MBA (no late hrs/weekend till EOM Sep.)
Layan Sooriyaarachchi | Unavailable | Pending allocation, working in EAG.
Mayuri Hewage | Available | ISTQB Foundation (December) | 4+ yrs ( Covance, MDS, Seimons, NetJets) | None | Manual Testing | None | Telcom-1yrTo3yrs | Healthcare-1yrTo3yrs | None | Yes-3<PrjLvlOnly>6 | Domain | None | Oracle DB Testing | Getting a billable allocation | Data warehousing | On leave from 28th Oct - 6th Nov
Hiroshani Ekanayaka | Available | ISTQB Foundation (December) | 1+ yrs | None | Manual Testing | None | None | Insurance<1yr | None | None | None | None | SOUP UI | Getting a billable allocation on Automation project | Automation | leave planned on 1st n last week of Dec
Lakmali Rajaguru | Available | Virtusa Scrum Master (Sep?) | Total 1.5yrs (VTAF, WSO2, Crico) | None | Manual Testing | VTAF | BFS<1yr | Insurance<1yr | None | None | None | None | VTAF, SOUP UI | Getting a billable allocation | Automation | None
Yasitha Bandara | Available | Virtusa Scrum Master (Sep?) | Total 1yr (Covance, NYL) | None | Manual Testing | None | Insurance<1yr | None | None | None | None | None | SOUP UI | Getting a billable allocation on Automation project | Automation | Expecting to move into a automation role
From 8/29 - Bench Report
Nipun Suriyaarachchi | Available | ISTQB Foundation (December) | Total 1.9 yrs (Kahaba 4mths, BT 1.5yrs.) | None | Manual Testing | Performance | Telcom-1yrTo3yrs | Healthcare<1yr | None | None | None | None | SOUP UI | Getting a billable allocation in Performance track | Security testing | None
Hasanga Dilrukshi | Available | Virtusa Scrum Master (Sep?) | Total 3 yrs. (EAG, Akura, Kahaba, Micros) | None | Manual Testing | None | EAG | Healthcare<1yr | None | Yes-PrjLvlOnly<3 | SMTC Project creation | None | ORACAL SQL DB Testing | Getting a billable allocation | Performance | Cannot work long hours due to a medical condition
Gowrybalan Balasubramaniam | Unavailable | Allocated to a project before Initial Assessment (BT-L2C T&M + LSA)
From 9/5 - Bench Report
Hiroshani Ekanayaka | Unavailable | 2nd time in bench report. Pending allocation (extend), working in netjets.
Mayuri Hewage | Unavailable | 2nd time in bench report. Pending allocation (extend), working in netjets.
Jeya Prathap | Unavailable | Pending allocation (extend), working in netjets.
Janani Nirasha Amarasingha | Unavailable | 2nd time in bench (Initial assessment already conducted), Allocation received back to MIT project on 9/5.
Dakshina Amarasinghe | Available | ISTQB Foundation (December) | Total 5 yrs (Aetna, Telerex, Senior Linc ) | None | Manual Testing | Automation (QTP) | Healthcare-3yrTo5yrs | None | None | None | None | None | SOUP UI, SQL DB Testing | Getting a billable allocation in a technical project | Performance & Automation testing | would like to work on HealthCare projects. Would prefere projects without late night work due to medical concerns
Sujitha Pathmanathan | Available | ISTQB Advance (December) | Total 3.5yrs (NYL-2.5, Taylor, AIG) | None | Manual Testing | Automation (selenium) | Insurance-1yrTo3yrs | None | Yes<3 | Yes-6<PrjLvlOnly>10 | Project related trainings | ISTQB - Foundation | SOUP UI, SQL DB Testing | Getting a billable allocation | Performance | None
Geeshani Madurangi Gunathilaka | Available | ISTQB Foundation (December) | Total 5.4 yrs (UTC, Affinion, MIT, Crico, MDS) | None | Manual Testing | None | BFS-1yrTo3yrs | Telcom<1yr | None | Yes-PrjLvlOnly<3 | Domain trainings | Virtusa Scrum master | None | Getting a billable allocation | Automation | On Bench from 1st of Sep. Have nominations for Crico, Critical Alert & CITI. Has a leave plan for 2.5 weeks in Dec.
Premkumar Premje | Available | ISTQB Foundation (December) | Total 4 yrs 3 Mon (NYL, Srilankan Airlines, Taylor, Cahaba, Covance,Gcom, Affinion, MDS) | None | Performance testing | Manual Testing | Insurance-1yrTo3yrs | Telcom<1yr | None | None | None | None | Performance testing | Getting a billable allocation on Performance testing | Performance testing | Planning to do ISTQB
Ruwanthi De Silva | Available | ISTQB Foundation (December) | Total 4 Yrs 3 mon (NYL,Aetna, PAP & PV, MDS) | None | Manual Testing | None | Insurance-1yrTo3yrs | Telcom-1yrTo3yrs | None | None | None | None | None | Getting a billable allocation | Automation | Planning to do ISTQB
Dilusha Lakmali | Available | ISTQB Foundation (December) | 2yrs including internship (Covance, BT - 1 month) | None | Manual Testing | None | Insurance<1yr | Telcom<1yr | None | None | None | None | Sellenium eclipse, VTAF | Getting a billable allocation | Mobility Testing | Planning to do ISTQB, intersted in Mobility testing
Anjula Gimhani Guruge | Available | Writing a white paper | Total 4 yrs 8 Mon (Aetna, Crico, Phillips) | None | Manual Testing | None | Healthcare-1yrTo3yrs | Insurance<1yr | None | Yes-PrjLvlOnly<3 | Domain trainings on Phillips | None | None | Getting a billable allocation | Mobility | Scrum master sessions attended but final presentation not complete. 14 days leave from 14th Sep
Dilsha Tharanga | Available | ISTQB Foundation (December) | Total 3.9 yr(Pat&whtny, NYL, FDC, Phillips | None | Manual Testing | None | Healthcare-1yrTo3yrs | BFS<1yr | None | None |  | Virtusa Scrum master | None | Getting a billable allocation | Automation | Planning to do ISTQB, Future allocation 1st Oct- Dec31st
Inoka Peiris | Available | ISTQB Foundation (December) | Total 10 yr (BT, PAT&Whitney, Mc Donalds, MTF, Phillips) | None | Manual Testing | Automation - QTP | Telcom>5yrs | BFS-1yrTo3yrs | Yes-3to6 | Yes-Prj&Org<3 | Testing Fundamentals for onboarding & RBT Trainings for interns | None | Automation - QTP | Getting Healthcare domain experience | Mobility Testing | Planning to do ISTQB, Future allocation 1st Oct- Dec31st
Dulani Eranthika Perera | Available | Due to go on Maternity leave from 1st week of Oct | Total 3.8 yrs (NYL CAS, Micros) | None | Manual Testing | None | Insurance-1yrTo3yrs | BFS-1yrTo3yrs | None | Yes-PrjLvlOnly<3 | Domain trainings | None | SOAP UI | Getting a billable allocation on an automation project | Automation
Wageesha Lakshan | Available | No experience in a project. | 4 months | None | Automation | None | None | None | None | None | None | None | Automation - Selenium Web driver (0 experience) | Getting a billable allocation on an automation project | Performance testing | None
Janna Junaideen | Available | Track change from ASM to QA | 3+ yrs (BT) | None | Manual Testing | None | Telcom-1yrTo3yrs | BFS<1yr | None | None | None | None | None | Want to get established in QA track | Automation | Self studying Jmeter and Sellenium. Planning to do ISTQB in Dec 2016. Working in ATP project without allocation
Dhanushka Mallawaarachchi | Available | Awaiting allocation for BT WLMS | 2 yrs (WLMS) | None
Nuwan Galkissa Mudalige | Available | Conducting Performance trainings | 7.5 yrs (Aetna) | None | Performance testing | Manual | Insurance-3yrTo5yrs |  | Yes-3to6
Chathurika Senanayake | Available | ISTQB Foundation (December) | 1 yr 2 months (VTAF, Taylor automation team) | None | Automation | Manual | Healthcare<1yr | Telcom<1yr | None | None | None | None | VTAF and Robot framework | Getting a billable allocation on an automation project | Manual Testing | On bench from 21st Sep. Nominated for Veracode.
Yvonne Jayaweera | Available | ISTQB Foundation (December) | 3 yrs (Aetna) | None | Manual Testing | None | Insurance-1yrTo3yrs | None | None | None | None | Virtusa Scrum master | None | Getting a billable allocation | Manual Testing | On bench from 15th Sep.
Githmini De Alwis | Available | ISTQB Foundation (December) | 8 yrs (Aetna, PNO, NYL, MDS) | None | Manual Testing | Automation | Insurance-3yrTo5yrs | Telcom-1yrTo3yrs | Yes-3to6 | Yes-6<PrjLvlOnly>10 | Domain and QA concepts | None | QTP, BB Macros, Soap UI | Getting a billable allocation & onsite exp | Improve Automation knowledge & exp | Leave planned from Oct 20- 31st
Vidya Yohendra | Available | Initial Assessment not complete
Shanthi Karunarathna | Available | Initial Assessment not complete | [13 empty] | Available from 24th Oct
Tharanga Kodippiliarachchi | Available | Initial Assessment not complete
Viduranga Gunarathna | Available | Awaiting allocation for HealthFirst
Viranthi Perera | Available | Awaiting onsite opportunity | 6 yrs (VQMF, Phillips, Semens, HomeServe) | Yes | Manual Testing | None | Healthcare-1yrTo3yrs | Insurance<1yr | None | None | None | ISTQB - Foundation | Soap UI, CTI | Getting billable allocation onsite | Mobility
Yasodha Nuwanthi Rathnayaka | Available | ISTQB Foundation (December) | 3.5 yrs (VTAF, Aetna, Micros, MDS | None | Manual Testing | VTAF | Telcom-1yrTo3yrs | Insurance-1yrTo3yrs | None | None | None | None | VTAF, SOUP UI | Getting a billable allocation on an automation project | Mobility & Automation
Thisara Madushanka Ranasinghe | Available | Allocated to HealthFirst (Customer Engagement) from 24th Oct
Isuri Wimarsha Boteju | Available | ISTQB Foundation (December) | 6 yrs (ERA insight, NYL, Aetna) | None | Manual Testing | None | None | Insurance<1yr | None | None | None | None | DB testing, Deplyment & Configuration testing | Getting a billable allocation | Automation testing
Sahani Sulochana Alwis | Available | ISTQB Foundation (December) | 3.5 yrs (semens, Micros) | None | Manual Testing | None | BFS-1yrTo3yrs | Telcom<1yr | None | Yes-PrjLvlOnly<3 | Domain trainings | None | None | Getting a billable allocation | Automation testing
Marie Dhamithree Sashikala Samaranayake | Available | ISTQB Foundation (December) | 5yrs (Aetna, Micros, MDS) | None | Manual Testing | None | Insurance-1yrTo3yrs | BFS-1yrTo3yrs | None | None | None | None | None | Getting a billable allocation & training on Perfromance & Automation testing | Performance & Automation Testing | None
Thilak Kulasekara | Available | ISTQB Foundation (December) | 6 yrs (Aetna, Covance, Crico) | None | Performance testing | Manual | Healthcare-3yrTo5yrs | Insurance<1yr | None | Yes-Prj&Org<3 | Load runner testing | None | Load runner | Getting a billable allocation on a performace project | Jmeter testing | Interested in Jmeter support testing
Menupa Dilushini Samarawickrama | Available | ISTQB Foundation (December) | 5 yrs (UTC, Phiilips, NYC-CAS) | None | Manual Testing | None | Healthcare-1yrTo3yrs | Insurance-1yrTo3yrs | None | None | None | None | Soap UI, DB testing | Getting a billable allocation | Mobility & Automation | Planning to do ISTQB
Anjula Alahakoon | Available | ISTQB Foundation (Dec) | 4 + yrs (BT, AIG Simons) | None | Manual Testing | None | Telcom-1yrTo3yrs | Insurance<1yr | None | Yes-PrjLvlOnly<3 | Domain trainings | None | Soap UI, DB testing | Getting a billable allocation | Mobility Testing | Looking for ATC transfer to HYD
From 10/10 - Bench Report
Kanchana Kumari Wijewickrama | Unavailable | Allocated to Micros
Nadeera Hettiarachchi | Available | Self studying on Load runner, mind mapping a PEGA framwork using OSCAR | 5.5 yrs (Aetna) | 2 yrs | Manual Testing | Performane Testing | Insurance>5yr | None | Yes<3 | None | None | None | Load runner, Soap UI | Getting a billable allocation on Performance testing or onsite opportunity | Performance testing
Isuri Chinthika Amarasinghe | Available | ISTQB Foundation (December) | 9months (Aetna) | None | Manual Testing | None | Healthcare<1yr | None | None | None | None | None | None | Getting a billable allocation | None | Still on probation.
Kavija Senevirathne | Available | ISTQB Foundation (December) | 7 months (MIT, Aetna) | None | Manual Testing | None | Healthcare<1yr | BFS<1yr | None | None | None | None | None | Getting a billable allocation in an Automation project | Automation testing
Sithumini Rajapaksha | Available | ISTQB Foundation (December) | 2yrs (Aetna ) | None | Manual Testing | None | Healthcare-1yrTo3yrs | None | None | None | None | None | DB testing, Services testing, Accessibility tools | Getting a billable allocation & learn automation | Automation testing | None
Kushan Wijesundara | Available | Healthcare related document consolidation | 8.5 yrs (Aetna) | 3 + yrs | Manual Testing | None | Healthcare>5yrs | None | Yes<3 | None | None | None | ETL testing, Services testing | Getting onsite opportuinity | Automation testing
Devendri Vishvanatha Kumari Sarathchandra | Available | White paper writing | 5+ yrs ( City, Seimons, Telerex) | None | Manual Testing | None | BFS-3yrTo5yrs | Healthcare-1yrTo3yrs | Yes<3 | None | None | ISTQB - Foundation | PEGA testing | Getting a billable allocation in PEGA projects | Automation testing | Last 2 weeks in Dec on leave
Sashika Hiranya Samaragunaratne | Available | ISTQB Foundation (December) | 4 yrs (Mc donals, Veracode, Dell) | None | Automation | Manual | Security Domain | None | None | None | none | None | Selenium, Python & Java | Getting a billable allocation | Automation testing | None
Chamindi Caldera | Available | ISTQB Foundation (December) | 2.5 yrs | None | Manual Testing | None | Healthcare-1yrTo3yrs | None | None | None | None | None | DB Testing using RAMBA | Getting a billable allocation | Automation Sellenium | None
Lakshitha Karagaswewa | Available | Assigned to BT WLMS awaiting allocation
Nadeesha Hansanie Hettiarachchi | Available | ISTQB Foundation (December) | 4 yrs (NYL) | None | Manual Testing | VTAF | Insurance-3yrTo5yrs | None | None | Yes-3<PrjLvlOnly>6 | Domain trainings | None | Security Testing | Getting a billable allocation | Mobility Testing | Just after maternity.Not willing to join projects with late night work
From 10/17 - Bench Report
Niluka Monnankulama | Available | ISTQB Foundation (December) | 6 months (MIT -rigor, NYL) | None | Manual Testing | None | Insurance<1yr | None | None | None | None | None | None | Getting a billable allocation in Healthcare or Telecom Domian | Automation Testing - Selenium
Viraj Jayasuriya | Unavailable | Initial Assessment not complete
Rasika Sanjeewanee Jayawardena | Available | Self studying on SAOP UI and TestComplete | 2 yrs (BT, HealthFirst) | None | Manual Testing | Automation - Selenium | Telcom-1yrTo3yrs | Healthcare<1yr | Yes-3to6 | Yes-3<Prj&Org>6 | Org - Test Design/ Proj - Domain | ISTQB - Foundation & Scrum Alians certification | Jmeter, Selenium, Services testing | Getting an Onsite opportunity and progressing for the next level | Mobility Testing | Planned leaves in Nov for 12 days intermitten
Sivakumaran Bhairavi | Available | Self studying on BA track change | 2 yrs (Mc Donalds, CRICO, EAG, CITI - 1.5 months) | None | Manual Testing | None | Pricing Sheet - EAG | Insurance<1yr | None | None | None | None | None | Getting a billable allocation & dual role to act as a BA | Business Analysis | Request to change tracks to BA
Piyumi Jayasinghe | Unavailable | Will be assigned to SriLankan Airlines
Mawroof Manas | Available | Self studying on improving Jmeter knowledge | 4.5 yrs (Mc Donalds, Lavastorm, Covance, Seimens) | None | Manual Testing | Performance & Automation | Telcom-1yrTo3yrs | Insurance<1yr | None | Yes-Prj&Org<3 | Jmeter | ISTQB - Foundation | Jmeter, Selenium, Load runner, Junit | Getting a billable allocation in Manual testing with a lead role and managing a team | None | Would like to work on an onsite opportunity
From 10/24 - Bench Report
Hansana Mendis | Available | Nominated to CITI | 6 months (NYL-AARP) | None | Manual Testing | None | Insurance<1yr | None | None | None | None | None | None | Getting a billable allocation | Automation testing | Experiemced in Java. So would like to be on a Automation project
Kusum Carmon Nanayakkara | Available | 2nd time in Bench report. Assessment was done previously
Supun Gunasinghe | Unavailable | Initial Assessment not complete
Chandima Wijebandara Athapattu | Unavailable | Initial Assessment not complete
Hirunika Wickramasinghe | Available | Nominated for HealthFirst from Nov 7th
Hiroshani Ekanayaka | Available | 3rd time in bench report. Pending allocation (extend), working in netjets.
Harsha Jayawilal | Unavailable | Out of the country
Heshani Subasinghe | Available | ISTQB Foundation | 6yrs ( Allair, BT WLMS, McDonalds, Gowireless) | None | Manual Testing | None | Healthcare-1yrTo3yrs | BFS-1yrTo3yrs | None | Yes-PrjLvlOnly<3 | Domain trainings | None | None | Getting a billable allocation in maintenance project | Automation testing | Under medication for Back pain
Piyumi Muthukumarana | Available | Allocated to Micros from Oct 25th
Dhammika Munasinghe | Available | Initial Assessment not complete
Charutha Fonseka | Available | Nominated to Aetna from Nov 7th
From 11/03 - Bench Report
Chathurika Nivanthi Vidanage | Unavailable | Allocated to NTB (November 15th onwareds)
Devindya Nagahawatta | Available | Selennium Automation & ISTQB | 3+ | None | Manual Testing | Insuarance domin - Claim System | Micros - Resturant | Insurance<1yr | None | Yes-3<PrjLvlOnly>6 | None | None | None | willing to train for Automation | Automation testing | None
Rangika Perera | Unavailable | Maternity Leave
Rinusha Wickramasinghe | Available | ISTQB Foundation /Mobility Training/Virtusa Scrum Master | 10 | None | Manual Testing | Automation -QTP | Healthcare>5yrs | BFS-3yrTo5yrs | Yes<3 |  |  | None | QTP | Getting a billable allocation in maintenance project | Mobility Testing | Last weeks in Dec on leave
Shashikala Thangawelu | Available | Virtusa Scrum Master | 2 yrs | None | Manual Testing | Automation - Selenium | Telcom-1yrTo3yrs | Healthcare<1yr | None |  |  |  | Selenium | Getting a billable allocation in Manual testing or automation | Automation testing | Last weeks in Dec on leave/ Planning to change tracks to BA
Sheron Gerard Jeshuran Logitharajah | Available | Coduting trainings (Security testing) | 3.6 yrs | None | Security testing | Performance & Functional testing | Telcom-1yrTo3yrs | BFS-1yrTo3yrs | None |  | Security/Performance Testing |  | Load Runner/Jmeter | Looking for onsite opportunity | Security/Performance Testing
Thulini Dissanayake | Unavailable | Allocated to NYL
Nilaksha Bastian | Available | Presented to HF | 4 yrs | None | Manual Testing | Automation -QTP | Healthcare-1yrTo3yrs |  | None |  |  |  | QTP | Getting a billable allocation in maintenance project | Security/Automation Testing
Hemal Nishantha | Available | Presented to JLT UK | 3.8 yrs | None | Manual Testing |  | Healthcare-3yrTo5yrs |  | None |  |  | ISTQB - Foundation |  | Looking for onsite opportunity | Mobility Testing
Tharmikka Tharmathas | Unavailable | Offline 19 days
Note on B2: For next 6 months
Note on H11: Rasika Suriarachchi: Hotel Management
Note on M11: Rasika Suriarachchi: Sun certified Java programmer
Note on H13: But, Mostly worked on Akura
Note on I28: Rasika Suriarachchi: Transportation
Note on H64: Janani Amarasingha: WSO2 Connector

## Training Attendance
Resource Name | Selenium Automation Training | [5 empty] | Healthcare Training | [6 empty] | Resource Name | Telecom Training | [8 empty] | Insurance Domain Training |  |  |  | Mobility Testing training
| Count |  | 10 | 11 | 10 | 6 | Count |  | 11 | 12 | 14 | 10 | 6 |  | Count | 1 | 0 | 0 | 0 | 0 |  |  | 0 | Count | 17 | 16 | 0 | Count | 23 | 19 | 17 | 0 | 0
| Trainer |  | Abdul Kareem | Abdul Kareem | Abdul Kareem | Abdul Kareem | Trainer |  | Tharanga Kodippiliarachchi | Dilini Liyanapatabendi | Amila Dantanarayana | Kanishka Dilrukshi Gamage | Zahir Hussain Muhammed Zaumer |  | Trainer | Pavithra Kankanamage | Saumika | Pavithra | Nisadi Wanigabandu | Nadeeka | Nadeeka | Inoka | Nisadi | Trainer | Subhotav Gosh | Subhotav Gosh | Subhotav Gosh | Trainer | Chanaka Ratnaweera | Chanaka | Chanaka | Chanaka | Chanaka
| Invited | % Attended | 2016-07-26 | 2016-07-28 | 2016-08-02 | 2016-08-11 | Invited | % Attended | 2016-08-03 | 2016-08-12 | 2016-08-19 | 2016-09-01 | 2016-09-08 |  | Invited | 2016-09-23 | 2016-09-29 | 2016-10-06 | 2016-10-13 | 2016-10-20 | 2016-10-27 | 2016-11-03 | 2016-11-10 | Invited | 2016-10-03 | 2016-10-04 | 2016-10-05 | Invited | 2016-10-19 | 2016-11-01 | 2016-11-03
Rangajith Lakmal Rajakaruna | Yes | 0% | CRICO support/ Later fully allocated. |  |  |  | Yes | 60% | A | N | A | A |  | Thushari Pinnaduwa | Yes | N | N | N | N |  |  |  |  | Yes | A
Dilini Liyanapatabendi | Yes | 50% | A | A | N | N | Yes | 20% | N | A | N | Allocated to Aetna DME PLUS |  | Mohamed Fulail | Yes | A | 80 | 100 | 70 | 90 | 100 |  |  | Yes | A | A
Neranjan Vidanagama | Yes | 75% | A | A | A | N | Yes | 100% | A | A | A | A | A | Harini Kandambi | Yes | 80 | N | N | N | 80 |  |  |  | Yes | A |  |  | Yes | A |  |  | TBD | TBD
Thushari Pinnaduwa | Yes | 100% | A | A | A | A | Yes | 100% | A | A | A | A | A | Nisadi Irushani Wanigabadu | Yes | 100 | 90 | 100 | T | 100 | 70 |  |  | Yes | A | A |  | Yes | A | A | A | TBD | TBD
Kanchana Jayalath | Yes | 0% | On maternity leave before the start |  |  |  | No | [6 empty] | Sabithini De Silva | Yes | N | N | 90 | 70 |  | 50 |  |  | Yes |  |  |  | Yes | A
Shanika Kavimini Pindeniya | Yes | 0% | N | N | N | N | Yes | 0% | N | N | N | N | N | Saumika Aberathna | Yes | 90 | T | 100 | 100 | 70 |  |  |  | Yes | A | A |  | Yes | A | A |  | TBD | TBD
Prasadie Lakmini Dharmasena | Yes | 0% | Allocated to a project before the start |  |  |  | No | [6 empty] | Maduri Nisansala Jayawickrama | Yes | N | N | N | N |  |  |  |  | Yes
Mohamed Fulail | Yes | 0% | N | N | N | N | Yes | 80% | A | N | A | A | A | Sashi Mekala De Alwis | Yes | 70 | N | 80 | N | 80 |  |  |  | Yes | A | A |  |  |  | A |  | TBD | TBD
Kalhari Jayasinghe | Yes | 0% | On maternity leave before the start |  |  |  | No | [6 empty] | Pavithra Kankanamge | Yes | T | 100 | T | 100 | 100 | 90 |  |  | Yes | A | A |  | Yes | A | A | A
Madhushika Wijenayaka | Yes | 0% | N | N | N | N | Yes | 0% | N | N | N | N | On maternity | Nadeeka Samanthi Wijewantha | Yes | 100 | 80 | 100 | 100 |  |  |  |  | Yes | A | A |  | Yes | A | A | A | TBD | TBD
Shanthiruban Balasubramaniam | Yes | 75% | A | A | A | Allocated to VTAF | Yes | 20% | A | Allocated to VTAF |  |  |  | Nirmana Gunasekara | Yes | N | N | N | N |  |  |  |  | Yes
Channa Gunasekera | Yes | 0% | CITI support/ Later fully allocated. |  |  |  | Yes | 0% | CITI support/ Later fully allocated. |  |  |  |  | Jayasanka Nimanthi | Yes | N | N | N | N |  | 100 |  |  | Yes | A | A
Rashmi Pathirana | Yes | 0% | N | N | N | N | Yes | 0% | CITI support/ Later fully allocated. |  |  |  |  | Kanishka Dilrukshi Gamage | Yes | 50 | N | 80 | 90 | 90 |  |  |  | Yes |  | A |  |  |  |  | A
Anushika Gunaratne | Yes | 0% | CRICO support/ Later fully allocated. |  |  |  | Yes | 0% | CRICO support/ Later fully allocated. |  |  |  |  | Hasari Wasana | Yes | N | 80 | 90 | N | 90 |  |  |  | Yes | N | A |  | Yes | A | A | A
Asiri Manoja | Yes | 0% | CRICO support/ Later fully allocated. |  |  |  | No | [6 empty] | Hasanga Dilrukshi | Yes | N | 80 | 90 | 80 | 80 |  |  |  | Yes | A | A |  | Yes | A | A
Nadeera Prashanthi Jayathilake | Yes | 0% | N | N | N | N | Yes | 40% | A | N | N | A | N | Sujitha Pathmanathan | Yes | 80 | N | Allocated for HealthFirst | [5 empty] | Yes | [7 empty] | TBD | TBD
Roshini Fernando | Yes | 75% | A | A | A | Attended SCRUM Training | Yes | 60% | A | A | A | N | Allocated to EAG | Premkumar Premje | Yes | N | 90 | N | 80 |  |  |  |  | Yes |  | A |  | Yes | A |  |  | TBD | TBD
Harini Kandambi | Yes | 100% | A | A | A | A | Yes | 0% | N | N | N | N | N | Dilsha Tharanga | Yes | 90 | 80 | 80 | N |  | 60 |  |  | Yes | A |  |  | Yes | A | A |  | TBD | TBD
Mohamed Aashik | Yes | 25% | A | N | N | N | Yes | 60% | A | N | A | A | Allocated to Citi | Inoka Peiris | Yes | 100 | 100 | 100 | 100 | 100 | 70 |  |  | Yes | A | A |  | Yes | A | A | A | TBD | TBD
Achani Wickramasinghe | Yes | 0% | N | N | N | N | Yes | 0% | N | N | N | Allocated to MIT Leadership QA |  | Dulani Eranthika Perera | Yes | N | N | N | N | On meternity leave |  |  |  | Yes | A
Abdul Kareem | Yes | 100% | A | A | A | A | Yes | 20% | N | N | A | Allocated to Project |  | Abdul Kareem | Yes | N | N | N | 100 | 90 |  |  |  | Yes |  | A | [5 empty] | TBD | TBD
Nisadi Irushani Wanigabadu | Yes | 0% | N | N | N | N | Yes | 80% | A | A | A | A | N | Wageesha Lakshan | Yes | N | N | N | N |  |  |  |  | Yes | [7 empty] | TBD | TBD
Wageesha Gamage | Yes | 100% | A | A | A | A | No | [6 empty] | Janani Nirasha Amarasingha | Yes | Not inbench during this time |  |  | 100 | 80 |  |  |  | Yes | A | A
Dilini Kulasuriya | Yes | 100% | A | A | A | A | No | [6 empty] | Janna Junaideen | Yes | 70 | 80 | N | N |  |  |  |  | Yes |  |  |  | Yes | A
Reza Thebuwana | No | 25% | N | N | A | N | No | [6 empty] | Dilusha Lakmali | Yes | N | N | [6 empty] | Yes
Gayani Jayarathna | Was not in bench, active participation | 100% | Invited after 1st session | A | A | A | No | [6 empty] | Nuwan Galkissa Mudalige | Yes | N | N | N | N |  | 90 |  |  | Yes |  |  |  | Yes |  | A | A
Mihikala Wijesekara | Was not in bench | 25% | N | A | N | N | No | [6 empty] | Chathurika Nethmini Senanayake | Yes | N | N | N | 90 |  | 90 |  |  | Yes
Sabithini De Silva | No | [5 empty] | Yes | 80% | A | A | A | N | A | Yvonne Jayaweera | Yes | N | 80 | 100 | 90 |  |  |  |  | Yes | A | A |  |  |  | TBD | TBD | TBD | TBD
Duminda Pathirana | No | [5 empty] | Yes | 20% | A | N | N | Allocated to Citi |  | Ruwanthi Desilva | Yes |  | N | [6 empty] | Yes | A
Hasini Lakmali Gunawardena | No | [5 empty] | No | [5 empty] | TBD | Dilusha Lakmali | Yes | N | N | [6 empty] | Yes | A | A |  |  |  | TBD | TBD | TBD | TBD
Heshani Laknilu Subasinghe | No | [5 empty] | Yes | 0% | N | N | N | Not available after 8/22 onwards |  | Puvanathakshini Vijayaratnam | Yes |  |  | 90 | 70 | 90 | [7 empty] | Yes | A |  | A
Anuradha Rathnayake | No | [5 empty] | Yes | 0% | N | N | N | N | N | Anjula Alahakoon | Yes | Not inbench during this time |  | 80 | 90 | 80 | [7 empty] | Yes | A | A | TBD | TBD | TBD
Maheesha Seneviratne | No | [5 empty] | Yes | 20% | N | A | N | N | N | Githmini DeAlwis | Yes | Not inbench during this time |  | 100 | 90 | [8 empty] | Yes | A | A | A | TBD | TBD
Saumika Aberathna | No | [5 empty] | No | 100% |  | A | A | A | A | Thisara Madushanka Ranasinghe | Yes | Not inbench during this time |  | 100 | 90 | [10 empty] | TBD | TBD | TBD | TBD
Pavithra Kankanamge | No | [5 empty] | No | 75% |  | A | A | A | N | Viduranga Gunarathne | Yes | Not inbench during this time |  |  | 100 | [10 empty] | TBD | TBD | TBD | TBD
Sashika Paranamanage | No | [5 empty] | Yes | 50% |  | A | A | Allocated to Citi ICG TTS RPA Prod Trail |  | Anjula Guruge | Yes | Not inbench during this time |  |  | 80
Maduri Jayawickram | No | [5 empty] | Yes | 75% |  | A | A | N | A | Nadeesha Hettiarachi | Yes | Not inbench during this time |  |  | 80 | [8 empty] | Yes | A | TBD | TBD | TBD | TBD
Sashi De Alwis | No | [5 empty] | Yes | 75% |  | A | A | A | N | Nadeera Hettiarachi | Yes | Not inbench during this time |  |  | 90 | 90 | 90 | [8 empty] | TBD | TBD | TBD | TBD
[14 empty] | Thilak Kulasekara | Yes | Not inbench during this time |  |  | 90 |  | 80
[14 empty] | Kavija Senevirathne | Yes | Not inbench during this time |  |  | 100
[14 empty] | Chathurika Senanayake | Yes | Not inbench during this time |  |  | 90
[14 empty] | Viranthi Perera | Yes | Not inbench during this time |  |  | 60 |  | 80 | [6 empty] | Yes | A
[14 empty] | Mayuri Hewage | Yes | Not inbench during this time |  |  | 90 |  | 90 | [6 empty] | Yes | A
[14 empty] | Vidya Yohendra | Yes | Not inbench during this time |  |  | 90
[14 empty] | Marie Dhamithree Sashikala Samaranayake | Yes | Not inbench during this time |  |  | 90 |  | 70 | [6 empty] | Yes | A | A | A
[14 empty] | Isuri Wimarsha Boteju | Yes | Not inbench during this time |  |  | 80 | 70 | [7 empty] | Yes | A | A | A
[14 empty] | Sahani Alwis | Yes | Not inbench during this time |  |  | 90
[14 empty] | Shanuka De silva | Yes | Not inbench during this time |  | 80 | N | 90 | 80 | [6 empty] | Yes |  | A | A
[14 empty] | Devendri Sarathchandra | Yes | Not inbench during this time |  | 90 | N | [10 empty] | A
[14 empty] | Shanthi Karunaratna | Yes | Not inbench during this time |  | 90 | N |  | 90
[14 empty] | Menupa samarawickrama | Yes | Not inbench during this time |  | 80 | N |  | 70 | [6 empty] | Yes | A |  | A
[14 empty] | Rinusha Wickramasinghe | [13 empty] | Yes | A | A
[14 empty] | Kusum Nanayakkara | [6 empty] | 90 | [6 empty] | Yes | A | A | A
[14 empty] | Tharanga Kodippiliarachchi | [5 empty] | 80 | [7 empty] | Yes |  | A
[14 empty] | Hiroshani Ekanayaka | [7 empty] | 70 | [5 empty] | Yes |  |  | A
[14 empty] | Yashoda rathnayaka | [5 empty] | 50 | 70 | [6 empty] | Yes |  |  | A
[14 empty] | Sithumini Rajapaksha | [5 empty] | 50 | [7 empty] | Yes |  |  | A
[14 empty] | Zaumer Hussain | [5 empty] | 70 | 90
[14 empty] | Bhairavi sivakumaran | [5 empty] | 90
[14 empty] | Hirunika Wickramasinghe | [6 empty] | 70
[14 empty] | Chathura Fonseka | [6 empty] | 90
Note on I5: Busy/Allocated to crico, still managed to attend trainings.
Note on R7: Harini Kandambi: Working on Presale
Note on S7: Harini Kandambi: Working on Presale
Note on T7: Harini Kandambi: Working on Presale
Note on R15: Harini Kandambi: Working on Presale
Note on S15: Harini Kandambi: Allocated to project
Note on R16: Harini Kandambi: Sick leave
Note on Q19: Harini Kandambi: Couldn’t attend due to Jmeter trainings
Note on R20: Harini Kandambi: allocated to project
Note on S24: Harini Kandambi: on Maternity leave
Note on R26: Harini Kandambi: Allocated to project
Note on S28: Harini Kandambi: Helping a project
Note on T28: Harini Kandambi: Helping a project
Note on S29: Harini Kandambi: Attrition risk
Note on Q30: Harini Kandambi: Conducting Jmeter trainngs during same time slot
Note on S30: Harini Kandambi: allocated to a proj
Note on Q32: Harini Kandambi: Not in Bench
Note on S33: Harini Kandambi: Assigned to project
Note on S34: Harini Kandambi: listed under attrition
Note on R35: Harini Kandambi: Not in Bench
Note on S39: Harini Kandambi: Not in bench

## Process
Bench Management Process
1 | Assign a lead to coordinate and track Bench work. Lead will be a T1/T2 resource from available bench. This role will be given to another resource when this lead get allocated a project. Also assign a secondary lead to support the lead and to cover up in absence of the lead.
2 | When a resource come in to bench, gather information on his/her interests, skills, gaps, career plans and accordingly plan relevant bench work for the resource with mutual understanding. Assign work to start after 1 weeks being in the bench.
3 | Continuously track progress of tasks. Help resources to overcome any blocking issues.
4 | Weekly circulate bench work tracking sheet and a summary view to QA and RM leadership.
5 | When complete a task by a resource, assign a rating by evaluating the work and taking feedback from relevant stakeholders. Keep the resource inform in advance on evaluation criteria and process.
6 | Use bench work evaluation records as input for MBO assessments.
7 | Track in the 'Comments' column the actual start date, end date for Presales and Project support works. This information can be used to provide PU exceptions whenever possible.
8 | Once a resource allocated to a billable project, move the work tracking record to 'Archive' tab and keep for future reference.
Instructions for the Lead
1 | When a resource coming in to bench have a productive discussion with the resource. Identify strengths, weaknesses, consider any PIPs in progress, interests and career plans and assign relevant work items.
2 | When bench resource proposed for a project and if get rejected, look for the rejected reasons and direct them to required trainings and bench work items. Consider the trainings done by QA practice as well as L&D training schedules.
3 | When a resource complete any work item, evaluate the work and assign a rating for it. Use the standard ratings same as MBO evaluations (O, EEC, MAES, NI, NA). For each work item use the evaluation criteria defined in 'Work List' tab. Record the rating and relevant comments in the 'Comments' column in the Work Tracking sheet.
4 | For each evaluation criteria consider the following aspects. Meeting timelines: Completing tasks within agreed timelines. Quality of work: consider review feedback and amount of rework. Stakeholder feedbacks: Consider feedback from * Presales: Presale owner/PM, QA Manager * Project support: PM, QA Lead * Participate Trainings: Trainer * Conduct Trainings: Participants (through feedback forms) * Conduct QA talks: Participants (through feedback forms) * Writing White papers/Blogs/ Articles: SME Review comments, Reader comments * Conduct Rigor projects for new joiners: Team members (through feedback forms) * Create domain specific test assets: Domain assets owner Commitment: Dedication and interest shown towards the task Availability & punctuality: Availability to attend to the task, Punctuality in attending to work and providing updates, Formal communication of unavailabilities/leaves. Focus on career progression: Understanding own strengths and weaknesses, working towards addressing the weaknesses, Proactively getting ready for next level. Value of the knowledge shared to QA community:

## Work List
Work List
# | Tasks | Evaluation criteria applicability
|  | Meeting timelines | Quality of work | Stakeholder feedbacks | Commitment | Availability & punctuality | Focus on career progression | Value of the knowledge shared to QA community
1 | Presales of new logos | √ | √ | √ | √ | √
2 | Support projects at risk (Code Red/Critical engagements) | √ | √ | √ | √ | √
3 | Participating Trainings o Performance testing o Test Automation o Security testing o Domain KTs | √ |  | √ | √ | √ | √
4 | Conducting Trainings | √ | √ | √ | √ | √ | √ | √
5 | Obtaining Certifications o ISTQB - Foundation o ISTQB - Advanced o Virtusa Scrum master | √ |  |  | √ | √ | √
6 | Conduct QA talks | √ | √ | √ | √ | √ | √ | √
7 | Writing White papers/Blogs/ Articles on QA topics | √ | √ | √ | √ | √ | √ | √
8 | Conduct Rigor projects for new joiners | √ | √ | √ | √ | √
9 | Create domain specific test assets (mind maps/ workflows/ scenarios) | √ | √ | √ | √ | √ |  | √